## Slide 1: IT Department Budget Guidelines: Supplement
IT Budget Transfer Essentials
November 2026 Kickoff
Notes: This document is a supplement to the IT Department Budget Guidelines. It is the reference for GDS teams carrying out the IT budget transfer, starting with next fiscal year's budget, as part of their day-to-day work. The budget transfer is not a project, and no dedicated organization will be set up. Follow the company-wide policy that has been decided; agree everything else with your counterpart Function.

## Slide 2: Where This Document Fits
Supplements the IT Department Budget Guidelines only where the IT budget transfer needs it
Company-wide Budgeting Guidelines
Company-wide
Company-wide budgeting rules. The IT budget transfer was decided here
IT Department Budget Guidelines
GDS
GDS budgeting principles and operations
This document: Supplement (IT Budget Transfer Essentials)
GDS teams
Transfer policy, approach and role template. Anything beyond the policy is agreed with each Function
Rules for using this document
If this document conflicts with the Guidelines, the Guidelines prevail
For GxP work, the SOPs and procedures set by Quality Assurance prevail. Use the roles in this document as a template
Below this document: the charter, runbook and budget transfer sheet. Record agreements in the agreement document

## Slide 3: What This Document Covers
Three things each team needs to know to carry out the budget transfer
1
Understand this term's goal
Transfer approval granted by end of December, and how to get there
2
Changes in roles after the transfer
Division of roles between the Functions and GDS (RACI)
3
IT asset management
Ownership of fixed assets and depreciation (held by GDS, which holds the budget)

## Slide 4: This Term's Goal
This term we aim for approval by end of December. Creating value from the transfer will be considered next term
Premises
Decided as company-wide policy
Decided by management and stated in the company-wide budgeting guidelines
Covers all departments except Sales (incl. HR, GA and Finance). All have been informed
Scope: budgets, contracts and admin work for business applications and related tools
Policy
Budgets fall into three groups by timing
Move together on Jan 1, 2027
Operating expense budgets (maintenance, licenses, cloud fees, outsourcing)
Held by GDS from next FY
Budgets for IT investment projects starting next year
Timing agreed case by case
IT investment projects continuing from this year (acquired assets, CIP, started work). Confirm with Finance (slide 7)
GDS
After the transfer,
handle step by step
Transitional: Work needing a formal procedure to change owners (SOP revision, GxP change control) stays with the current owner until done. Record it and its due date in the agreement
Contracts: Signatory changes to GDS at next renewal. Notify suppliers of the new invoice addressee by early February
Goal: transfer approval granted by end of December
Notes: This term's goal is to have the transfer approval granted by the end of December. Creating value from the transfer will be considered next term. Budgets are split into three groups by when they move: operating expense budgets move together on January 1; budgets for IT investment projects starting next year are held by GDS from next year's budget; and for IT investment projects continuing from this year, the timing is agreed case by case. For the goal, check separately what must be done by the end of December and what will be handled step by step after the transfer.

## Slide 5: November–December Schedule (Indicative)
November
December
January onward
11/2
11/9
11/16
11/23
11/30
12/7
12/14
12/21
12/28
1/1 onward
Milestones
November
Kickoff
12/11
Agreement
12/18
Ready
12/31
Approval
1/1
Transfer
S&G
Publish and explain the supplement
Check transfer status and progress (daily)
Cross-check agreement documents
Draft and approve the transfer request (per Function)
Assigned BP
① Agree with the Function (interview sheet → agreement)
② Take over (manuals, contracts, past records)
③ Report completion (at approval request)
Update the progress tracker (ongoing)
Report and consult on issues (ongoing)
Change owner of transitional work (after procedure)
Per due dates
S&G: transfer approval is granted
Agreements and completion reports for all cases are in
The progress tracker (transfer status) is up to date
Approval information (budgets and contracts, next year's budget) is in order
Assigned BP: ready to start the work after the transfer
An approved agreement (budgets and contracts, work to take over, reporting route, timing)
Manuals, contracts and past records have been taken over
GDS can manage contracts and pay from January
Notes: This is the indicative schedule for November and December. The assigned BP agrees with the transferring Function based on the interview sheet, takes over the work based on work manuals, contracts and past records, and reports completion when the approval request is submitted. Throughout the period, keep the progress tracker up to date, and report and consult whenever a problem occurs or is foreseen. The goal for S&G is that the transfer approval is granted; the goal for the assigned BP is being ready to start the work after the transfer. Both require the materials needed to reach that state.

## Slide 6: Roles After the Transfer (RACI)
In IT-led domains, GDS leads (R) and decides (A) with the Functions' advice (C)
Exception: systems specific to one Function with no impact on others
Business strategy
Business
Business direction (create, grow, sustain, shrink/exit), business issues and expectations of IT
IT strategy
IT-led
IT investment policy, enterprise architecture and shared platforms, technology choices and sourcing direction
System requirements
IT-led
Functional, non-functional and transition requirements
Solution
IT-led
SaaS, package or custom build; lifecycle to retirement
Vendor
IT-led
Suppliers, proposals and terms; performance and risk
Business requirements
Business
Purpose and outcomes of change; business needs and priorities
Business benefits
Business
Actual investment returns (KPIs) and factors limiting value
Clarify needs
Evaluate / review
Develop IT strategy
Apply policy
Requirements definition
Solution selection
Vendor selection
Accept / measure benefits
Non-functional reqs
Sourcing
Business
R, A: Functions
IT-led
R, A: GDS C: Functions
GDS
management
(A, R)
IT financial management
Budget planning and execution, cost visibility by Function and project, comparing investment benefits with costs
Contract management
Agreeing and revising terms for licenses, cloud, maintenance and outsourcing
Service quality management
Agreeing and monitoring service levels, validation, and change control (incl. GxP)
Notes: This is the division of roles after the transfer. Boxes are domains; the labels on the arrows are actions. The Functions clarify needs from the business strategy, define business requirements, and evaluate acceptance and benefit results to review the strategy. GDS leads, and decides with the Functions' advice, on: developing the IT strategy from the business strategy, applying its policy to solutions, setting non-functional requirements, setting the sourcing policy for vendors, requirements definition, solution selection and vendor selection. Systems specific to one Function with no impact on others are an exception. GDS is responsible for IT financial management, contract management and service quality management. Confirm the details and the timing of GDS taking over in the agreement document for each case.

## Slide 7: Fixed Assets Are Held by GDS, Which Holds the Budget
GDS also manages assets and depreciation; R&D and manufacturing costs are allocated to the benefiting Function
Type of IT investment | CIP | Fixed asset account (asset owner = bears depreciation) |  | 
 |  | Single Function | Shared (multiple) | Enterprise-wide
① New business app (package, configured) | GDS | GDS | GDS | N/A
② Custom business app / add-on | GDS | GDS | GDS | N/A
③ Upgrade of existing asset (capex) | GDS | GDS | GDS | GDS
④ Perpetual software license | None | GDS | GDS | GDS
⑤ Hardware and equipment | None | GDS | GDS | GDS
⑥ Platforms and shared services (cloud, data) | GDS | N/A | GDS | GDS (not in scope)
Assets held or in progress at the time of transfer
① Acquired assets
Capitalized at transfer, with depreciation started
② Construction in progress (CIP)
Recorded as CIP at transfer, to be capitalized next year
③ Started, not yet in CIP
Work started but nothing yet recorded as CIP
All move to GDS. Agree the timing with the transferring Function and confirm with Finance so the accounting is handled correctly

## Slide 8: Next Actions (November)
After the kickoff, start with these three things
Assigned BP
Start agreeing with the transferring Function using the interview sheet
Assigned BP
Fill in your row of the progress tracker so you can update the transfer status
Assigned BP
List IT investment projects continuing from this year (acquired, CIP, started) and set up a check with Finance
Final deadline: December 31 — transfer approval
Notes: After the kickoff, please start with three things: begin agreeing with the transferring Function based on the interview sheet; fill in your row of the progress tracker so you can update the transfer status; and identify IT investment projects continuing from this year and set up a check with Finance. The final deadline is December 31: approval of the transfer.