## Slide 1: IT Budget Transfer Kickoff
Briefing for all IT staff
November 2, 2026 | Budget Transfer Lead
Notes: Today's briefing gives everyone in IT a shared understanding of the IT budget transfer that starts with next year's budget. We will share what has been decided and how we will proceed through the end of December.

## Slide 2: First, Answers to Two Concerns
Concern 1
Are there exceptions?
Does work that needs
a formal procedure
also move in January?
No exceptions. All budgets move at once on January 1, 2027
No individual transfers and no cases on hold. The transfer is decided company policy
Where the current owner is fixed in approved documents such as SOPs, rules or segregation of duties, and changing it needs a formal procedure (e.g., GxP change control), the current owner continues until the procedure is complete (interim measure)
The budget moves even with an interim measure. That work and its planned completion are recorded in the agreement document
Concern 2
After the transfer,
who does what?
What happens to the
departments' authority?
Accountability (A) stays with departments. Roles are agreed from a standard RACI
IT takes over indirect work (budget management, contracts, ordering, receiving and payment) from January
A for direct and IT-related work stays with the Business Owner. IT does not take over A
Per case, only the R / C split on IT-related work and when IT starts taking R can change. The transferring manager approves the agreement document to finalize it (slides 6-8)
Notes: Before the main topic, let me answer what matters most to both IT staff and the business side. First, there are no exceptions: all budgets move at once on January 1. Only work whose owner is fixed in approved documents and needs a formal procedure to change stays with the current owner until the procedure is complete, but the budget still moves. Second, accountability (A) stays with the departments. IT takes on indirect work and the hands-on part of IT-related work. What can change per case is limited, and the transferring manager finalizes it by approving the agreement document.

## Slide 3: This Term's Goal
Transfer approvals (ringi) completed by the end of December
This term we aim for transfer approval by end of December. How to create value from the transfer will be considered next term.
What has been decided
Decided as company policy
Decided by management and stated in the company-wide budgeting guidelines
Covers all departments except Sales (including HR, General Affairs and Finance). All departments have been informed
Scope: budgets, contracts and indirect work for business applications and related tools
Company-wide domains such as infrastructure and security are out of scope
Business ownership stays with the departments
Everything transfers at once
Budgets move on January 1, 2027
There is no decision on whether to transfer
Bulk transfer: January 1, 2027 (all budgets)
Interim measure: where the current roles (Before) are fixed in approved documents or records such as SOPs, rules or segregation of duties, and changing them needs a formal procedure (e.g., GxP change control), the current owner continues until the procedure is complete
Even with an interim measure, the budget moves on January 1
Interim-measure work and its planned completion are recorded in the agreement document
Goal for end of December
Approval of the ringi. Not everything has to be finished
Only three prerequisites
1. Information needed for the ringi (transfer decision, next year's budget, agreement document) is organized
2. What is not yet finished (SOP revisions, change of contract signatory, etc.) is clear for each case
3. IT can start managing contracts and payments from January
No contract procedures at the time of transfer. The signatory changes to IT at the next renewal; vendors are notified of the new invoice addressee by early February
Roles from next year onward are shown on slides 6-8 for reference. For now, please focus on the budget transfer
Notes: This term's goal is to have the transfer ringi approved by the end of December. How to create value from the transfer will be considered again next term. The transfer is decided company policy, and all budgets move at once on January 1. Work whose owner is fixed in approved documents stays with the current owner as an interim measure until the procedure is complete, but the budget still moves. Not everything has to be finished by the end of December; there are only three prerequisites.

## Slide 4: Tasks for November-December
Nov
Dec
Jan onward
11/2
11/9
11/16
11/23
11/30
12/7
12/14
12/21
12/28
1/1-
Milestones
11/2
Kickoff
12/11
Agreement due
12/18
Ready
12/31
Ringi approved
1/1
Transfer (indirect work starts)
Transfer Lead
Hold the kickoff
Check transfer status and progress (daily)
Cross-check agreement documents
Raise and approve transfer ringi (by department)
Case Owners
1. Resolve pending decisions and finish the inventory
2. Agree on handover and IT-related work (agreement document)
3. Hand over indirect work to the receivers
4. Confirm readiness
Update transfer status (as needed)
Change owner of interim-measure work (after procedure)
Per planned completion
Transfer Lead (1 person)
Drives the whole effort. Checks transfer status daily and raises the transfer ringi once all of a department's cases have a status. Cross-checks agreement documents. Handles requests to and consultation with the Head of IT
Case Owner (usual contact)
The IT member who already acts as the business department's counterpart for the case. Does the case-level work and requests approval from the transferring manager (slide 5)
Notes: These are the tasks for November and December. Case owners work through steps 1 to 4 in order: the inventory in November, the agreement by December 11, and steps 3 and 4 by December 18. The transfer lead checks status daily and raises the ringi as each department's case statuses are filled. From January, only the completion of owner-change procedures (such as GxP change control) for interim-measure work remains.

## Slide 5: Guide for Case Owners
What to do (tasks 1-4 on slide 4)
1
Resolve pending decisions and finish the inventory
By end Nov
Confirm entries with the department contact, fill in missing inputs and clear all pending decisions
Deliverable Budget transfer sheet confirmed by the department contact (budget list, links, systems, work, contracts), with no pending decisions / Status → Inventoried
2
Agree on handover and IT-related work
By 12/11
Customize the RACI (slides 7-8) for the case, add interim measures and the handover method, and get the transferring manager's approval
Deliverable Approved agreement document (customized RACI, interim measures and planned completion, handover method; logged in the decision log) / Status → Agreed
3
Hand over indirect work to the receivers
By 12/18
Receive procedures and materials from the department and pass them to the receivers
Deliverable Full set of materials handed over (contract copies, billing contacts, payment timing, unpaid invoices). For work needing an owner-change procedure (e.g., GxP), its filing and planned completion
4
Confirm readiness
By 12/18
Use the readiness checklist to confirm the agreement document, handover and filing of interim-measure procedures
Deliverable Readiness checklist record / Status → Readiness
What we ask of you
Inventorying
Inventoried
Agreed
Readiness
There is also "Out of scope"
Update the transfer status in the budget transfer sheet each time its conditions are met
Update your own row in the "Progress" sheet (task status and completion date)
If the "Check (auto)" column shows a message, review the status (the transfer lead checks daily and will ask)
Decisions are calculated by formula. Do not overwrite them; fix the inputs instead
Record work whose owner is fixed in approved documents as an interim measure in the agreement document
If you may miss a deadline, tell the transfer lead the reason and outlook early
Notes: Case owners, please keep this slide at hand. It matches tasks 1 to 4 on slide 4, each with a deliverable. Progress is managed in the budget transfer sheet, so update the status each time its conditions are met.

## Slide 6: Three Layers of Work and Roles
Indirect work transfers. IT-related work (middle layer) is agreed case by case. In every layer, final accountability (A) stays with the Business Owner
BO Business Owner
Department head. Owns the business process and the need, purpose and benefits of applications
BU Business User
Department staff. Use the system for their work, raise requests and confirm acceptance
SO System Owner
IT. Responsible for system availability, maintenance and security. Does not take over A
Direct work
Not transferred
A
Decides business requirements and acceptance
R
Work using the system, organizing requirements, acceptance checks
C
Consulted
IT-related work
Middle layer. Agreed per case
A
Decisions and approvals (not negotiable)
R / C
Explains needs and benefits
R
Does the hands-on work (investment: planning, quotes, application; expense: monitoring, improvement, contract review)
Indirect work
Transferred (previously done by departments)
I
Informed
—
Not involved
A / R
Budget management, contracts, ordering, receiving and payment (from January)
For IT-related work, customize the RACI templates on slides 7-8 per case, agree with the transferring manager and keep it as a document
Reference (GxP): EU GMP Annex 11 (2011; 2025 draft revision), PIC/S PI 011-3, MHLW Guideline on Management of Computerized Systems
Reference (internal control): FSA Standards and Practice Standards for Management Assessment and Audit of ICFR; METI System Management Standards Supplement (IT Control Guidance for Financial Reporting) and System Management Standards
Notes: We think of work in three layers. Direct work is the department's own work, so it does not move. Indirect work is the procedure that comes with the budget, so it moves to IT. IT-related work, in between, is handled by customizing the RACI templates on the next two slides for each case, agreeing with the transferring manager and keeping it as a document. In every layer, final accountability (A) stays with the Business Owner.

## Slide 7: RACI: IT Investment Process (Before → After)
BO: Business Owner (dept. head) BU: Business User SO: System Owner (IT) R: Responsible A: Accountable C: Consulted I: Informed
Activity | Layer | Before (current) |  | After (post-transfer) |  | 
 |  | BO | BU | BO | BU | SO
I-1 Identify issues and needs | Direct | A | R | A | R | C
I-2 Define business requirements | Direct | A | R | A | R | C
I-3 Evaluate solutions (system approach, fit with existing systems) | IT-rel. | A | R | A | C | R
I-4 Gather vendor information and quotes | IT-rel. | A | R | A | C | R
I-5 Estimate benefits and costs (BU: benefits, SO: costs) | IT-rel. | A | R | A | R | R
I-6 Prepare budget request and investment application | IT-rel. | A | R | A | C | R
I-7 Approve the investment | — | A | R | Approver (under review in new IT governance tiers) |  | 
I-8 Select vendor | IT-rel. | A | R | A | C | R
I-9 Conclude contract | Indirect | A | R | I |  | A/R
I-10 Ordering, receiving and payment | Indirect | A | R |  |  | A/R
I-11 Run the project (progress, quality) | IT-rel. | A | R | A | R | R
I-12 Acceptance (meets business requirements?) | Direct | A | R | A | R | C
I-13 Review benefits (post-implementation) | IT-rel. | A | R | A | R | C
Before: the business side does the work alone (one pattern in this first version). If a case's actual Before differs, rewrite it before comparing
After: IT becomes more involved; A for direct and IT-related work stays with the BO. Shaded cells change from Before (blank means no longer involved)
Per-case customization: only the R / C split between BU and SO on IT-related rows, and when SO takes on R, may change. The A column and the direct/indirect rows are fixed
Notes: This is the RACI for the IT investment process. For most IT-related work, SO takes R for the hands-on work and BO focuses on A for decisions and approvals. IT handles indirect work. In each case agreement, confirm the current way of working as Before, list the differences from After, and agree how R is held. That A stays with the BO is not subject to agreement.

## Slide 8: RACI: Expense Process (Before → After)
BO: Business Owner (dept. head) BU: Business User SO: System Owner (IT) R: Responsible A: Accountable C: Consulted I: Informed
Activity | Layer | Before (current) |  | After (post-transfer) |  | 
 |  | BO | BU | BO | BU | SO
E-1 Work using the system | Direct | A | R | A | R | 
E-2 Department-run operations (user and access management) | Direct | A | R | A | R | C
E-3 Budget planning and spend control | Indirect | A | R | I |  | A/R
E-4 Contract renewal, change and termination procedures | Indirect | A | R | C |  | A/R
E-5 Receive and pay invoices | Indirect | A | R |  |  | A/R
E-6 Instruct vendors and receive reports (contract management) | Indirect | A | R |  |  | A/R
E-7 Monitor operations (SLA, incidents, usage) | IT-rel. | A | R | A | C | R
E-8 Improvement (BU: requests, SO: triage and delivery) | IT-rel. | A | R | A | R | R
E-9 Contract review (usage, license count, alternatives, renewal decision) | IT-rel. | A | R | A | C | R
E-10 Evaluate vendors | IT-rel. | A | R | A | C | R
E-11 GxP change control | IT-rel. | A | R | A | R | R
Before: the business side does the work alone (one pattern in this first version). If a case's actual Before differs, rewrite it before comparing
After: IT becomes more involved; A for direct and IT-related work stays with the BO. Shaded cells change from Before (blank means no longer involved)
Per-case customization: only the R / C split between BU and SO on IT-related rows, and when SO takes on R, may change. The A column and the direct/indirect rows are fixed
E-11 normally also requires Quality Assurance involvement (omitted in this table)
Notes: This is the RACI for the expense process. IT takes over indirect work from January. For IT-related work such as monitoring, improvement and contract review, SO does the hands-on work and decisions stay with the BO.