## Field_Definitions
GDS Budget Ledger – Field Definitions / 項目定義
How to use / 使い方
• | Opex_Budget is the only place where budgets are entered. It will be locked once the budget is final. |  |  | 予算を入れる場所はOpex_Budgetだけです。予算確定後はロックされます。
• | Actuals: the budget manager pastes the accounting data as values at the end of the table every month, with import_batch set to the closing month. |  |  | Actuals：予算管理者が毎月、会計データを表の末尾に値で貼り付けます。import_batchには締め月を入れます。
• | Budget_vs_Actual: set fiscal_year, close_month and display_currency at the top. Owners enter only the Forecast (input) and Rationale rows (light blue cells). |  |  | Budget_vs_Actual：上部で会計年度・締め月・表示通貨を指定します。責任者が入力するのは見込み入力行と理由行（薄い青のセル）だけです。
• | Monthly order (budget manager, Excel desktop): 1) on Prior_Forecast, right-click the table > Refresh; 2) paste the new actuals into Actuals; 3) advance close_month. Always refresh Prior_Forecast before pasting actuals. See the monthly runbook for details. |  |  | 毎月の手順（予算管理者、デスクトップ版Excel）：①Prior_Forecastの表を右クリック＞更新 ②新しい実績をActualsに貼り付ける ③締め月を進める。Prior_Forecastの更新は必ず実績の貼り付けより前に行う。詳細は月次運用手順書を参照。
• | If a check at the top of Budget_vs_Actual is not 0, some budget or actual rows have no block. Ask IT Finance to add the cost center and account. |  |  | Budget_vs_Actual上部のチェックが0でない場合、ブロックのない予算・実績があります。ITファイナンスにコストセンター・勘定科目の追加を依頼してください。
• | Use Sheet View (View > Sheet View) to filter or sort, so other users are not affected. |  |  | 絞り込み・並べ替えは「シートビュー」（表示＞シートビュー）で行い、他の人の表示を変えないでください。
• | Enter one record per row. Do not insert blank rows, merge cells or change column headers. |  |  | 1行に1件を入力します。空行の挿入、セルの結合、列見出しの変更はしないでください。
• | Yes = required. Yes* = required depending on the type (see description). Use the dropdowns for List fields. |  |  | Yes＝必須。Yes*＝種別によって必須（説明を参照）。List型はプルダウンから選びます。
• | Dates: YYYY-MM-DD. Amounts: excluding tax, in the currency of the row. Do not convert currencies. |  |  | 日付はYYYY-MM-DD。金額は税抜で、その行の通貨のまま入力します。換算はしないでください。
• | The Example column shows the expected format only. Do not copy example values. |  |  | Example列は入力形式の例です。例の値を転記しないでください。
• | Grey sheets (Cost_Centers, Accounts, FX_Rates, Lists) are copies of the master data file and must not be edited. To get the latest values, open in Excel desktop and click Data > Refresh All (not needed every time). To add or change values, ask IT Finance. |  |  | グレーのシート（Cost_Centers・Accounts・FX_Rates・Lists）はマスタファイルの写しで、編集しません。最新にするときはデスクトップ版Excelで「データ＞すべて更新」を押します（毎回は不要）。値の追加・変更はITファイナンスに依頼してください。
Sheets / シート一覧
Sheet | Maintained by | Purpose (EN) |  | 目的（日本語）
Opex_Budget | Input | All budgets of GDS. Fixed (locked) once the budget is final. One row per fiscal year. |  | GDSの予算をすべて集約するシート。予算確定後は固定（ロック）する。1行＝1会計年度
Actuals | ITF only | Actuals downloaded from each region's accounting system, pasted monthly by the budget manager. |  | 各リージョンの会計システムからダウンロードした実績。予算管理者が毎月貼り付ける
Dashboard | Auto (do not edit) | Overview: KPIs, region x sub-function, monthly trend and the largest variances. Follows the settings at the top of Budget_vs_Actual. |  | 全体像：KPI、リージョン×サブファンクション、月次推移、差異の大きい項目。Budget_vs_Actual上部の設定（年度・締め月・通貨）に連動する
Budget_vs_Actual | Auto (do not edit) / Forecast & Rationale: Input | Budget, actual and actual + forecast by cost center and account, with variances and rationale. Budget and actual are filled automatically. |  | コストセンター×勘定科目ごとの予算・実績・実績＋見込みと、差異・理由。予算と実績は自動で表示される
Prior_Forecast | ITF only | Snapshot of the Actual + Forecast rows, refreshed by Power Query before new actuals are pasted. Feeds the Prior Month Forecast row. |  | 実績＋見込み行の控え。新しい実績を貼り付ける前にPower Queryで更新する。前月見込みの行に表示される
Opex_Budget — Input
Sheet | Field (EN) | 項目名（日本語） | Type | Required | Example | Description (EN) | 説明（日本語）
Opex_Budget | fiscal_year | 会計年度 | Integer | Yes | 2027 | Fiscal year (January to December). | 会計年度（1月〜12月）
Opex_Budget | region | リージョン | List | Yes | JP | Region of the cost center. JP / NA / EMEA. | コストセンターのリージョン。JP／NA／EMEA
Opex_Budget | owner | 入力責任者 | Text | Yes | T. Yamada | Person responsible for keeping this row up to date. | この行を最新に保つ責任者
Opex_Budget | budget_id | 予算ID | Text | No | BT-0012 | Optional ID to identify the budget line (e.g. budget transfer case ID, internal budget number). | 予算行を識別する任意のID（予算移管の案件ID、社内の予算番号など）
Opex_Budget | cost_center_code | コストセンター | List | Yes | JP-GDS-APP | Cost center that bears the cost. | 費用を計上するコストセンター
Opex_Budget | account_key | 勘定科目 | List | Yes | JP¦5101 | Local account of the region (format: region¦local code). | 当該リージョンの現地勘定科目（形式：リージョン¦現地科目コード）
Opex_Budget | cost_category | 費用区分 | List | Yes | SaaS / License | Nature of the cost, independent of the accounting account: SaaS / License, Maintenance, Outsourcing, Cloud, Telecom, Hardware, Personnel, Depreciation, Travel & Training, Other. | 会計上の勘定科目とは別に、費用の性質で分類する区分（SaaS・ライセンス、保守、業務委託、クラウド、通信、ハードウェア、人件費、減価償却、出張・研修、その他）
Opex_Budget | system_name | システム名 | Text | Yes | Salesforce | System the cost relates to. Use 'Common' for costs not tied to one system. | 費用が関係するシステム。特定のシステムに紐づかない費用は「Common」と書く
Opex_Budget | vendor_name | ベンダー名 | Text | Yes | Salesforce Japan | Vendor or supplier. Use 'Internal' for internal staff cost. | ベンダー・取引先。社内人件費は「Internal」と書く
Opex_Budget | expense_item | 費目 | Text | Yes | Domestic travel | What the budget is for. Several items may share the same cost center and account. | 予算の内容。同じコストセンター・勘定科目の中で複数に分けてよい
Opex_Budget | project_id | プロジェクトID | Text | Yes* | CAPEX-2027-014 | Capital investment budget number. *Required when the cost belongs to a project. | 設備投資予算の管理番号。※プロジェクト案件の費用の場合は必須
Opex_Budget | asset_id | 固定資産ID | Text | Yes* | FA-000123 | Fixed asset ID in the asset register. *Required for depreciation. | 固定資産台帳のID。※減価償却費の場合は必須
Opex_Budget | source_type | 入力元 | List | Yes | MANUAL | MANUAL = entered directly / CONTRACT, ASSET, WORKFORCE = pasted from the utility's Export sheet. | MANUAL＝直接入力／CONTRACT・ASSET・WORKFORCE＝ユーティリティのExportから貼り付けた行
Opex_Budget | currency | 通貨 | List | Yes | JPY | Currency of the amounts in this row. Do not convert. | この行の金額の通貨。換算しない
Opex_Budget | m01 | 1月 | Number | No | 500000 | Budget for month 1, excluding tax. | 1月の予算額（税抜）
Opex_Budget | m02 | 2月 | Number | No | 500000 | Budget for month 2, excluding tax. | 2月の予算額（税抜）
Opex_Budget | m03 | 3月 | Number | No | 500000 | Budget for month 3, excluding tax. | 3月の予算額（税抜）
Opex_Budget | m04 | 4月 | Number | No | 500000 | Budget for month 4, excluding tax. | 4月の予算額（税抜）
Opex_Budget | m05 | 5月 | Number | No | 500000 | Budget for month 5, excluding tax. | 5月の予算額（税抜）
Opex_Budget | m06 | 6月 | Number | No | 500000 | Budget for month 6, excluding tax. | 6月の予算額（税抜）
Opex_Budget | m07 | 7月 | Number | No | 500000 | Budget for month 7, excluding tax. | 7月の予算額（税抜）
Opex_Budget | m08 | 8月 | Number | No | 500000 | Budget for month 8, excluding tax. | 8月の予算額（税抜）
Opex_Budget | m09 | 9月 | Number | No | 500000 | Budget for month 9, excluding tax. | 9月の予算額（税抜）
Opex_Budget | m10 | 10月 | Number | No | 500000 | Budget for month 10, excluding tax. | 10月の予算額（税抜）
Opex_Budget | m11 | 11月 | Number | No | 500000 | Budget for month 11, excluding tax. | 11月の予算額（税抜）
Opex_Budget | m12 | 12月 | Number | No | 500000 | Budget for month 12, excluding tax. | 12月の予算額（税抜）
Opex_Budget | note | 備考 | Text | No |  | Free comment. | 備考
Actuals — ITF only
Sheet | Field (EN) | 項目名（日本語） | Type | Required | Example | Description (EN) | 説明（日本語）
Actuals | region | リージョン | List | Yes | JP | Region of the cost center. JP / NA / EMEA. | コストセンターのリージョン。JP／NA／EMEA
Actuals | fiscal_year | 会計年度 | Integer | Yes | 2027 | Fiscal year of the posting. | 計上の会計年度
Actuals | month | 月 | Integer | Yes | 4 | Posting month (1-12). | 計上月（1〜12）
Actuals | cost_center_code | コストセンター | Text | Yes | JP-GDS-APP | Cost center on the journal entry. | 仕訳に指定されたコストセンター
Actuals | local_account_code | 現地勘定科目コード | Text | Yes | 5101 | Account code in the region's accounting system (without region prefix). | リージョンの会計システム上の科目コード（リージョン接頭辞なし）
Actuals | currency | 通貨 | List | Yes | JPY | Currency of the posted amount. | 計上額の通貨
Actuals | amount | 金額 | Number | Yes | 98000 | Posted P&L amount, excluding tax. Credits as negative. | PL計上額（税抜）。貸方はマイナス
Actuals | description | 摘要・取引先 | Text | No | Microsoft | Optional, for investigating variances. | 任意。差異の調査用
Actuals | import_batch | 取込バッチ | Text | Yes | 202704 | YYYYMM of the closing month when the data was imported. | 取り込んだときの締め月（YYYYMM）
Budget_vs_Actual — Auto (do not edit) / Forecast & Rationale: Input
Sheet | Field (EN) | 項目名（日本語） | Type | Required | Example | Description (EN) | 説明（日本語）
Budget_vs_Actual | fiscal_year (C3) | 会計年度 | Integer | Yes | 2027 | Fiscal year to display. | 表示する会計年度
Budget_vs_Actual | close_month (C4) | 締め月 | Integer 1-12 | Yes | 6 | Last month with actuals. Months up to this month use actuals; later months use the forecast. | 実績がそろっている最後の月。この月までは実績、以降は見込みを使う
Budget_vs_Actual | display_currency (C5) | 表示通貨 | List | Yes | JPY | All amounts are converted to this currency at the budget rate (FX_Rates). | すべての金額をこの通貨に予算レート（FX_Rates）で換算して表示する
Budget_vs_Actual | cost_center_code / account_key | コストセンター／勘定科目 | Key | Yes | JP-GDS-APP / JP¦5101 | Set by IT Finance on the first row of each block after the budget is fixed. Other rows follow automatically. | 予算確定後、ITファイナンスが各ブロックの1行目に設定する。他の行は自動で連動する
Budget_vs_Actual | owner | 責任者 | Text | Yes | T. Yamada | Person who explains variances and maintains the forecast for this block. | このブロックの差異説明と見込み更新の責任者
Budget_vs_Actual | Budget | 予算 | Row (auto) | - |  | Sum of Opex_Budget for the cost center and account. | Opex_Budgetの該当コストセンター・勘定科目の合計
Budget_vs_Actual | Actual | 実績 | Row (auto) | - |  | Sum of Actuals. Shown up to close_month. | Actualsの合計。締め月まで表示
Budget_vs_Actual | Variance vs Budget | 差異（対予算） | Row (auto) | - |  | Months / YTD: Actual - Budget. MTG: forecast for the remaining months - Budget. FY = YTD + MTG. Positive = overspend. | 各月・YTD：実績−予算。MTG：残り期間の見込み−予算。FY＝YTD＋MTG。プラスは超過
Budget_vs_Actual | Forecast (input) | 見込み（入力） | Row (input) | No | 120000 | Expected amount for months after close_month. Leave blank to keep the budget amount. | 締め月より後の月の見込み額。空欄なら予算額のまま
Budget_vs_Actual | Actual + Forecast | 実績＋見込み | Row (auto) | - |  | Actual up to close_month (taken from the Actual row); after that, the Forecast (input) row above, or the budget if it is blank. | 締め月まではActual行の実績を転記、以降は直上の見込み入力行の値（空欄なら予算）
Budget_vs_Actual | Prior Month Forecast | 前月見込み | Row (auto) | - |  | Actual + Forecast as of the previous month, read from the Prior_Forecast sheet by cost center and account. | 前月時点の実績＋見込み。Prior_Forecastシートからコストセンター・勘定科目で引いて表示する
Budget_vs_Actual | Variance vs Prior Month | 差異（対前月見込み） | Row (auto) | - |  | (Actual + Forecast) - Prior Month Forecast. Shows how much the outlook moved this month. Positive = increase. | （実績＋見込み）−前月見込み。今月どれだけ見込みが動いたか。プラスは増加
Budget_vs_Actual | Rationale | 理由 | Row (input) | When variance | Invoice delayed | Month columns: reason for each month's variance. YTD column: comment on the year-to-date total. MTG column: comment on the remaining-period forecast (vs budget and vs prior month). | 月の列：各月の差異の理由。YTD列：累計に対するコメント。MTG列：残り期間の見込みに対するコメント（対予算・対前月）

## Dashboard
GDS Budget Dashboard / 予算ダッシュボード
Key figures / 主要指標
FY Budget | YTD Budget | YTD Actual | YTD Variance | FY Actual + Forecast | FY Variance vs Budget | FY Variance vs Budget (prior month) | Change vs Prior Month
通期予算 | 累計予算 | 累計実績 | 累計差異 | 通期着地見込み | 通期差異（対予算） | 前月時点の通期差異（対予算） | 前月からの変化
By region and sub-function / リージョン×サブファンクション別
Region | Sub-function | FY Budget | YTD Budget | YTD Actual | YTD Variance | FY Actual + Forecast | FY Variance | Change vs Prior
JP | Applications
JP | Infrastructure
JP | Data
JP | Security
JP | Governance
JP | Transferred (other functions)
JP | Subtotal
NA | Applications
NA | Infrastructure
NA | Data
NA | Security
NA | Governance
NA | Transferred (other functions)
NA | Subtotal
EMEA | Applications
EMEA | Infrastructure
EMEA | Data
EMEA | Security
EMEA | Governance
EMEA | Transferred (other functions)
EMEA | Subtotal
Total
Monthly budget vs actual / 月次の予算と実績
Month | Budget | Actual | Forecast | Variance %
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Bars: actual (dark) up to the close month, forecast (light) after. Dashed line: budget. Red line: (actual + forecast - budget) / budget on the right axis (±15%, 0 in the middle).
Largest variances vs budget (FY) / 対予算の差異が大きい項目（通期）
# | Cost center | Account | Owner | YTD Variance | MTG Variance | FY Variance | Rationale (YTD) | Rationale (MTG)
1
2
3
4
5
6
7
8
9
10

## Budget_vs_Actual
Budget vs Actual / 予実対比
fiscal_year |  | 2027 |  | FX factor to display currency (budget rate) |  |  |  |  | Checks (should be 0) / チェック（0であること）
close_month |  | 1 |  | JPY | USD | EUR | GBP |  | Budget not in any block / ブロック外の予算
display_currency |  | JPY | [6 empty] | Actual not in any block / ブロック外の実績
|  |  |  | Prior forecast as of close month / 前月見込みの基準月: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
region | cost_center_code | cost_center_name | account_key | account_name | owner | line | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YTD | MTG | FY | sub_function | function | abs_fy_var
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale

## Opex_Budget
fiscal_year | region | owner | budget_id | cost_center_code | account_key | cost_category | system_name | vendor_name | expense_item | project_id | asset_id | source_type | currency | m01 | m02 | m03 | m04 | m05 | m06 | m07 | m08 | m09 | m10 | m11 | m12 | note

## Actuals
region | fiscal_year | month | cost_center_code | local_account_code | currency | amount | description | import_batch

## Prior_Forecast
cost_center_code | account_key | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YTD | MTG | FY | as_of_close_month | Setup (IT Finance, once, Excel desktop) / 初回設定（ITファイナンス、1回だけ、デスクトップ版Excel）
1. Delete the placeholder table on the left. / 左の仮テーブルを削除する。
2. Data > Get Data > From Other Sources > Blank Query. Paste the M code below and name the query Prior_Forecast. / 空のクエリに下のMコードを貼り、クエリ名をPrior_Forecastにする。
3. Close & Load To > Existing worksheet > Prior_Forecast!$A$1. / 「閉じて次に読み込む」でこのシートのA1に読み込む。
4. Data > Queries & Connections > Prior_Forecast > Properties: uncheck 'Refresh this connection on Refresh All'. / 接続のプロパティで「すべて更新でこの接続を更新する」をオフにする。
let
Src = Excel.CurrentWorkbook(){[Name="rng_BvA"]}[Content],
Hdr = Table.PromoteHeaders(Src, [PromoteAllScalars=true]),
Rows = Table.SelectRows(Hdr, each [line] = "Actual + Forecast" and [cost_center_code] <> null and [cost_center_code] <> ""),
Keep = Table.SelectColumns(Rows, {"cost_center_code","account_key","Jan","Feb","Mar","Apr","May","Jun","Jul","Aug","Sep","Oct","Nov","Dec","YTD","MTG","FY"}),
Close = Excel.CurrentWorkbook(){[Name="prm_close_month"]}[Content]{0}[Column1],
Result = Table.AddColumn(Keep, "as_of_close_month", each Close, Int64.Type)
in
Result

## Cost_Centers
cost_center_code | cost_center_name | region | function | sub_function | active

## Accounts
account_key | region | local_account_code | local_account_name | global_coa_code | global_coa_name | mgmt_category

## FX_Rates
fiscal_year | rate_type | currency | rate_to_jpy

## Lists
region | currency | contract_type | employment_type | allocation_type | source_type | cost_category | rate_type | yes_no
JP | JPY | PREPAID | EMPLOYEE | COST_CENTER | MANUAL | SaaS / License | BUDGET | Y
NA | USD | MONTHLY | EXTERNAL | PROJECT | CONTRACT | Maintenance |  | N
EMEA | EUR | RATE_REF |  |  | ASSET | Outsourcing
| GBP |  |  |  | WORKFORCE | Cloud
Telecom
Hardware
Personnel
Depreciation
Travel & Training
Other