## Field_Definitions
GDS Budget Ledger – Field Definitions / 項目定義
How to use / 使い方
• | Opex_Budget is the only place where budgets are entered. It will be locked once the budget is final. |  |  | 予算を入れる場所はOpex_Budgetだけです。予算確定後はロックされます。
• | Actuals: the budget manager pastes the accounting data as values at the end of the table every month, with import_batch set to the closing month. |  |  | Actuals：予算管理者が毎月、会計データを表の末尾に値で貼り付けます。import_batchには締め月を入れます。
• | Budget_vs_Actual: set fiscal_year, close_month and display_currency at the top. Owners enter only the Forecast (input) and Rationale rows (light blue cells). |  |  | Budget_vs_Actual：上部で会計年度・締め月・表示通貨を指定します。責任者が入力するのは見込み入力行と理由行（薄い青のセル）だけです。
• | Monthly order (budget manager, Excel desktop): 1) on Prior_Forecast, right-click the table > Refresh; 2) paste the new actuals into Actuals; 3) advance close_month. Always refresh Prior_Forecast before pasting actuals. See the monthly runbook for details. |  |  | 毎月の手順（予算管理者、デスクトップ版Excel）：①Prior_Forecastの表を右クリック＞更新 ②新しい実績をActualsに貼り付ける ③締め月を進める。Prior_Forecastの更新は必ず実績の貼り付けより前に行う。詳細は月次運用手順書を参照。
• | If a check at the top of Budget_vs_Actual is not 0, some budget or actual rows have no block. Ask IT Finance to add the cost center and account. |  |  | Budget_vs_Actual上部のチェックが0でない場合、ブロックのない予算・実績があります。ITファイナンスにコストセンター・勘定科目の追加を依頼してください。
• | Use Sheet View (View > Sheet View) to filter or sort, so other users are not affected. |  |  | 絞り込み・並べ替えは「シートビュー」（表示＞シートビュー）で行い、他の人の表示を変えないでください。
• | Enter one record per row. Do not insert blank rows, merge cells or change column headers. |  |  | 1行に1件を入力します。空行の挿入、セルの結合、列見出しの変更はしないでください。
• | Yes = required. Yes* = required depending on the type (see description). Use the dropdowns for List fields. |  |  | Yes＝必須。Yes*＝種別によって必須（説明を参照）。List型はプルダウンから選びます。
• | Dates: YYYY-MM-DD. Amounts: excluding tax, in the currency of the row. Do not convert currencies. |  |  | 日付はYYYY-MM-DD。金額は税抜で、その行の通貨のまま入力します。換算はしないでください。
• | The Example column shows the expected format only. Do not copy example values. |  |  | Example列は入力形式の例です。例の値を転記しないでください。
• | Grey sheets (Cost_Centers, Accounts, FX_Rates, Lists) are copies of the master data file and must not be edited. To get the latest values, open in Excel desktop and click Data > Refresh All (not needed every time). To add or change values, ask IT Finance. |  |  | グレーのシート（Cost_Centers・Accounts・FX_Rates・Lists）はマスタファイルの写しで、編集しません。最新にするときはデスクトップ版Excelで「データ＞すべて更新」を押します（毎回は不要）。値の追加・変更はITファイナンスに依頼してください。
Sheets / シート一覧
Sheet | Maintained by | Purpose (EN) |  | 目的（日本語）
Opex_Budget | Input | All budgets of GDS. Fixed (locked) once the budget is final. One row per fiscal year. |  | GDSの予算をすべて集約するシート。予算確定後は固定（ロック）する。1行＝1会計年度
Actuals | ITF only | Actuals downloaded from each region's accounting system, pasted monthly by the budget manager. |  | 各リージョンの会計システムからダウンロードした実績。予算管理者が毎月貼り付ける
Dashboard | Auto (do not edit) | Overview: KPIs, region x sub-function, monthly trend and the largest variances. Follows the settings at the top of Budget_vs_Actual. |  | 全体像：KPI、リージョン×サブファンクション、月次推移、差異の大きい項目。Budget_vs_Actual上部の設定（年度・締め月・通貨）に連動する
Budget_vs_Actual | Auto (do not edit) / Forecast & Rationale: Input | Budget, actual and actual + forecast by cost center and account, with variances and rationale. Budget and actual are filled automatically. |  | コストセンター×勘定科目ごとの予算・実績・実績＋見込みと、差異・理由。予算と実績は自動で表示される
Prior_Forecast | ITF only | Snapshot of the Actual + Forecast rows, refreshed by Power Query before new actuals are pasted. Feeds the Prior Month Forecast row. |  | 実績＋見込み行の控え。新しい実績を貼り付ける前にPower Queryで更新する。前月見込みの行に表示される
Opex_Budget — Input
Sheet | Field (EN) | 項目名（日本語） | Type | Required | Example | Description (EN) | 説明（日本語）
Opex_Budget | fiscal_year | 会計年度 | Integer | Yes | 2027 | Fiscal year (January to December). | 会計年度（1月〜12月）
Opex_Budget | region | リージョン | List | Yes | JP | Region of the cost center. JP / NA / EMEA. | コストセンターのリージョン。JP／NA／EMEA
Opex_Budget | owner | 入力責任者 | Text | Yes | T. Yamada | Person responsible for keeping this row up to date. | この行を最新に保つ責任者
Opex_Budget | budget_id | 予算ID | Text | No | BT-0012 | Optional ID to identify the budget line (e.g. budget transfer case ID, internal budget number). | 予算行を識別する任意のID（予算移管の案件ID、社内の予算番号など）
Opex_Budget | cost_center_code | コストセンター | List | Yes | JP-GDS-APP | Cost center that bears the cost. | 費用を計上するコストセンター
Opex_Budget | account_key | 勘定科目 | List | Yes | JP¦5101 | Local account of the region (format: region¦local code). | 当該リージョンの現地勘定科目（形式：リージョン¦現地科目コード）
Opex_Budget | cost_category | 費用区分 | List | Yes | SaaS / License | Nature of the cost, independent of the accounting account: SaaS / License, Maintenance, Outsourcing, Cloud, Telecom, Hardware, Personnel, Depreciation, Travel & Training, Other. | 会計上の勘定科目とは別に、費用の性質で分類する区分（SaaS・ライセンス、保守、業務委託、クラウド、通信、ハードウェア、人件費、減価償却、出張・研修、その他）
Opex_Budget | system_name | システム名 | Text | Yes | Salesforce | System the cost relates to. Use 'Common' for costs not tied to one system. | 費用が関係するシステム。特定のシステムに紐づかない費用は「Common」と書く
Opex_Budget | vendor_name | ベンダー名 | Text | Yes | Salesforce Japan | Vendor or supplier. Use 'Internal' for internal staff cost. | ベンダー・取引先。社内人件費は「Internal」と書く
Opex_Budget | expense_item | 費目 | Text | Yes | Domestic travel | What the budget is for. Several items may share the same cost center and account. | 予算の内容。同じコストセンター・勘定科目の中で複数に分けてよい
Opex_Budget | project_id | プロジェクトID | Text | Yes* | CAPEX-2027-014 | Capital investment budget number. *Required when the cost belongs to a project. | 設備投資予算の管理番号。※プロジェクト案件の費用の場合は必須
Opex_Budget | asset_id | 固定資産ID | Text | Yes* | FA-000123 | Fixed asset ID in the asset register. *Required for depreciation. | 固定資産台帳のID。※減価償却費の場合は必須
Opex_Budget | source_type | 入力元 | List | Yes | MANUAL | MANUAL = entered directly / CONTRACT, ASSET, WORKFORCE = pasted from the utility's Export sheet. | MANUAL＝直接入力／CONTRACT・ASSET・WORKFORCE＝ユーティリティのExportから貼り付けた行
Opex_Budget | currency | 通貨 | List | Yes | JPY | Currency of the amounts in this row. Do not convert. | この行の金額の通貨。換算しない
Opex_Budget | m01 | 1月 | Number | No | 500000 | Budget for month 1, excluding tax. | 1月の予算額（税抜）
Opex_Budget | m02 | 2月 | Number | No | 500000 | Budget for month 2, excluding tax. | 2月の予算額（税抜）
Opex_Budget | m03 | 3月 | Number | No | 500000 | Budget for month 3, excluding tax. | 3月の予算額（税抜）
Opex_Budget | m04 | 4月 | Number | No | 500000 | Budget for month 4, excluding tax. | 4月の予算額（税抜）
Opex_Budget | m05 | 5月 | Number | No | 500000 | Budget for month 5, excluding tax. | 5月の予算額（税抜）
Opex_Budget | m06 | 6月 | Number | No | 500000 | Budget for month 6, excluding tax. | 6月の予算額（税抜）
Opex_Budget | m07 | 7月 | Number | No | 500000 | Budget for month 7, excluding tax. | 7月の予算額（税抜）
Opex_Budget | m08 | 8月 | Number | No | 500000 | Budget for month 8, excluding tax. | 8月の予算額（税抜）
Opex_Budget | m09 | 9月 | Number | No | 500000 | Budget for month 9, excluding tax. | 9月の予算額（税抜）
Opex_Budget | m10 | 10月 | Number | No | 500000 | Budget for month 10, excluding tax. | 10月の予算額（税抜）
Opex_Budget | m11 | 11月 | Number | No | 500000 | Budget for month 11, excluding tax. | 11月の予算額（税抜）
Opex_Budget | m12 | 12月 | Number | No | 500000 | Budget for month 12, excluding tax. | 12月の予算額（税抜）
Opex_Budget | note | 備考 | Text | No |  | Free comment. | 備考
Actuals — ITF only
Sheet | Field (EN) | 項目名（日本語） | Type | Required | Example | Description (EN) | 説明（日本語）
Actuals | region | リージョン | List | Yes | JP | Region of the cost center. JP / NA / EMEA. | コストセンターのリージョン。JP／NA／EMEA
Actuals | fiscal_year | 会計年度 | Integer | Yes | 2027 | Fiscal year of the posting. | 計上の会計年度
Actuals | month | 月 | Integer | Yes | 4 | Posting month (1-12). | 計上月（1〜12）
Actuals | cost_center_code | コストセンター | Text | Yes | JP-GDS-APP | Cost center on the journal entry. | 仕訳に指定されたコストセンター
Actuals | local_account_code | 現地勘定科目コード | Text | Yes | 5101 | Account code in the region's accounting system (without region prefix). | リージョンの会計システム上の科目コード（リージョン接頭辞なし）
Actuals | currency | 通貨 | List | Yes | JPY | Currency of the posted amount. | 計上額の通貨
Actuals | amount | 金額 | Number | Yes | 98000 | Posted P&L amount, excluding tax. Credits as negative. | PL計上額（税抜）。貸方はマイナス
Actuals | description | 摘要・取引先 | Text | No | Microsoft | Optional, for investigating variances. | 任意。差異の調査用
Actuals | import_batch | 取込バッチ | Text | Yes | 202704 | YYYYMM of the closing month when the data was imported. | 取り込んだときの締め月（YYYYMM）
Budget_vs_Actual — Auto (do not edit) / Forecast & Rationale: Input
Sheet | Field (EN) | 項目名（日本語） | Type | Required | Example | Description (EN) | 説明（日本語）
Budget_vs_Actual | fiscal_year (C3) | 会計年度 | Integer | Yes | 2027 | Fiscal year to display. | 表示する会計年度
Budget_vs_Actual | close_month (C4) | 締め月 | Integer 1-12 | Yes | 6 | Last month with actuals. Months up to this month use actuals; later months use the forecast. | 実績がそろっている最後の月。この月までは実績、以降は見込みを使う
Budget_vs_Actual | display_currency (C5) | 表示通貨 | List | Yes | JPY | All amounts are converted to this currency at the budget rate (FX_Rates). | すべての金額をこの通貨に予算レート（FX_Rates）で換算して表示する
Budget_vs_Actual | cost_center_code / account_key | コストセンター／勘定科目 | Key | Yes | JP-GDS-APP / JP¦5101 | Set by IT Finance on the first row of each block after the budget is fixed. Other rows follow automatically. | 予算確定後、ITファイナンスが各ブロックの1行目に設定する。他の行は自動で連動する
Budget_vs_Actual | owner | 責任者 | Text | Yes | T. Yamada | Person who explains variances and maintains the forecast for this block. | このブロックの差異説明と見込み更新の責任者
Budget_vs_Actual | Budget | 予算 | Row (auto) | - |  | Sum of Opex_Budget for the cost center and account. | Opex_Budgetの該当コストセンター・勘定科目の合計
Budget_vs_Actual | Actual | 実績 | Row (auto) | - |  | Sum of Actuals. Shown up to close_month. | Actualsの合計。締め月まで表示
Budget_vs_Actual | Variance vs Budget | 差異（対予算） | Row (auto) | - |  | Months / YTD: Actual - Budget. MTG: forecast for the remaining months - Budget. FY = YTD + MTG. Positive = overspend. | 各月・YTD：実績−予算。MTG：残り期間の見込み−予算。FY＝YTD＋MTG。プラスは超過
Budget_vs_Actual | Forecast (input) | 見込み（入力） | Row (input) | No | 120000 | Expected amount for months after close_month. Leave blank to keep the budget amount. | 締め月より後の月の見込み額。空欄なら予算額のまま
Budget_vs_Actual | Actual + Forecast | 実績＋見込み | Row (auto) | - |  | Actual up to close_month (taken from the Actual row); after that, the Forecast (input) row above, or the budget if it is blank. | 締め月まではActual行の実績を転記、以降は直上の見込み入力行の値（空欄なら予算）
Budget_vs_Actual | Prior Month Forecast | 前月見込み | Row (auto) | - |  | Actual + Forecast as of the previous month, read from the Prior_Forecast sheet by cost center and account. | 前月時点の実績＋見込み。Prior_Forecastシートからコストセンター・勘定科目で引いて表示する
Budget_vs_Actual | Variance vs Prior Month | 差異（対前月見込み） | Row (auto) | - |  | (Actual + Forecast) - Prior Month Forecast. Shows how much the outlook moved this month. Positive = increase. | （実績＋見込み）−前月見込み。今月どれだけ見込みが動いたか。プラスは増加
Budget_vs_Actual | Rationale | 理由 | Row (input) | When variance | Invoice delayed | Month columns: reason for each month's variance. YTD column: comment on the year-to-date total. MTG column: comment on the remaining-period forecast (vs budget and vs prior month). | 月の列：各月の差異の理由。YTD列：累計に対するコメント。MTG列：残り期間の見込みに対するコメント（対予算・対前月）

## Dashboard
GDS Budget Dashboard / 予算ダッシュボード
Key figures / 主要指標
FY Budget | YTD Budget | YTD Actual | YTD Variance | FY Actual + Forecast | FY Variance vs Budget | FY Variance vs Budget (prior month) | Change vs Prior Month
通期予算 | 累計予算 | 累計実績 | 累計差異 | 通期着地見込み | 通期差異（対予算） | 前月時点の通期差異（対予算） | 前月からの変化
By region and sub-function / リージョン×サブファンクション別
Region | Sub-function | FY Budget | YTD Budget | YTD Actual | YTD Variance | FY Actual + Forecast | FY Variance | Change vs Prior
JP | Applications
JP | Infrastructure
JP | Data
JP | Security
JP | Governance
JP | Transferred (other functions)
JP | Subtotal
NA | Applications
NA | Infrastructure
NA | Data
NA | Security
NA | Governance
NA | Transferred (other functions)
NA | Subtotal
EMEA | Applications
EMEA | Infrastructure
EMEA | Data
EMEA | Security
EMEA | Governance
EMEA | Transferred (other functions)
EMEA | Subtotal
Total
Monthly budget vs actual / 月次の予算と実績
Month | Budget | Actual | Forecast | Variance %
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Bars: actual (dark) up to the close month, forecast (light) after. Dashed line: budget. Red line: (actual + forecast - budget) / budget on the right axis (±15%, 0 in the middle).
Largest variances vs budget (FY) / 対予算の差異が大きい項目（通期）
# | Cost center | Account | Owner | YTD Variance | MTG Variance | FY Variance | Rationale (YTD) | Rationale (MTG)
1
2
3
4
5
6
7
8
9
10

## Budget_vs_Actual
Budget vs Actual / 予実対比
fiscal_year |  | 2027 |  | FX factor to display currency (budget rate) |  |  |  |  | Checks (should be 0) / チェック（0であること）
close_month |  | 6 |  | JPY | USD | EUR | GBP |  | Budget not in any block / ブロック外の予算
display_currency |  | JPY | [6 empty] | Actual not in any block / ブロック外の実績
|  |  |  | Prior forecast as of close month / 前月見込みの基準月: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
region | cost_center_code | cost_center_name | account_key | account_name | owner | line | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YTD | MTG | FY | sub_function | function | abs_fy_var
| JP-GDS-APP |  | JP¦5101 |  | owner: JP APP lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-GDS-APP |  | JP¦5103 |  | owner: JP APP lead; line: Budget
Actual
Variance vs Budget
[6 empty] | Forecast (input) | [6 empty] | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
[6 empty] | Rationale | [5 empty] | May-Jun: change requests for pricing module | [6 empty] | Overrun from May due to unplanned change requests | Change requests continue until Dec; vendor quote received
| JP-GDS-APP |  | JP¦5106 |  | owner: JP APP lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-GDS-DAT |  | JP¦5101 |  | owner: JP DAT lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-GDS-DAT |  | JP¦5103 |  | owner: JP DAT lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-GDS-GOV |  | JP¦5106 |  | owner: JP GOV lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-GDS-GOV |  | JP¦5107 |  | owner: JP GOV lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-GDS-GOV |  | JP¦5108 |  | owner: JP GOV lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-GDS-INF |  | JP¦5101 |  | owner: JP INF lead; line: Budget
Actual
Variance vs Budget
[6 empty] | Forecast (input) | [6 empty] | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
[6 empty] | Rationale | [5 empty] | Azure usage above commitment | [6 empty] | New analytics workloads | Usage stays ~30% above commit; commitment review in Q4
| JP-GDS-INF |  | JP¦5102 |  | owner: JP INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-GDS-INF |  | JP¦5104 |  | owner: JP INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-GDS-INF |  | JP¦5105 |  | owner: JP INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-GDS-INF |  | JP¦5106 |  | owner: JP INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-GDS-SEC |  | JP¦5101 |  | owner: JP SEC lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-GDS-SEC |  | JP¦5103 |  | owner: JP SEC lead; line: Budget
Actual
Variance vs Budget
[6 empty] | Forecast (input) | [6 empty] | 5200000 | 5200000 | 5200000
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
[6 empty] | Rationale | [5 empty] | Apr-Jun: unbudgeted incident response retainer | [6 empty] | Retainer not in budget; approved by CISO | Retainer continues until Sep, then ends
| JP-RND-200 |  | JP¦5102 |  | owner: R&D BP; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| JP-SLS-100 |  | JP¦5101 |  | owner: Sales BP; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-APP |  | NA¦6101 |  | owner: NA APP lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
[6 empty] | Rationale |  |  | Mar: CRM license true-up (+45 seats) | [9 empty] | True-up paid in March; no further true-up expected
| NA-GDS-APP |  | NA¦6103 |  | owner: NA APP lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-APP |  | NA¦6106 |  | owner: NA APP lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-DAT |  | NA¦6101 |  | owner: NA DAT lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-DAT |  | NA¦6103 |  | owner: NA DAT lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-GOV |  | NA¦6106 |  | owner: NA GOV lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-GOV |  | NA¦6107 |  | owner: NA GOV lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-GOV |  | NA¦6108 |  | owner: NA GOV lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-INF |  | NA¦6101 |  | owner: NA INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-INF |  | NA¦6102 |  | owner: NA INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-INF |  | NA¦6104 |  | owner: NA INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-INF |  | NA¦6105 |  | owner: NA INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-INF |  | NA¦6106 |  | owner: NA INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-SEC |  | NA¦6101 |  | owner: NA SEC lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| NA-GDS-SEC |  | NA¦6103 |  | owner: NA SEC lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-APP |  | EMEA¦7101 |  | owner: EMEA APP lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-APP |  | EMEA¦7103 |  | owner: EMEA APP lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-APP |  | EMEA¦7106 |  | owner: EMEA APP lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-DAT |  | EMEA¦7101 |  | owner: EMEA DAT lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-DAT |  | EMEA¦7103 |  | owner: EMEA DAT lead; line: Budget
Actual
Variance vs Budget
[6 empty] | Forecast (input) | [6 empty] | 1280000 | 1280000 | 1280000 | 1600000 | 1600000 | 1600000
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
[6 empty] | Rationale | [5 empty] | Project start delayed (vendor onboarding) | [6 empty] | Under-run: project started late | Ramp-up from Jul; expected to stay below budget
| EU-GDS-GOV |  | EMEA¦7106 |  | owner: EMEA GOV lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-GOV |  | EMEA¦7107 |  | owner: EMEA GOV lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-GOV |  | EMEA¦7108 |  | owner: EMEA GOV lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-INF |  | EMEA¦7101 |  | owner: EMEA INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-INF |  | EMEA¦7102 |  | owner: EMEA INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-INF |  | EMEA¦7104 |  | owner: EMEA INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-INF |  | EMEA¦7105 |  | owner: EMEA INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-INF |  | EMEA¦7106 |  | owner: EMEA INF lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-SEC |  | EMEA¦7101 |  | owner: EMEA SEC lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
| EU-GDS-SEC |  | EMEA¦7103 |  | owner: EMEA SEC lead; line: Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale
Budget
Actual
Variance vs Budget
Forecast (input)
Actual + Forecast
Prior Month Forecast
Variance vs Prior Month
Rationale

## Opex_Budget
fiscal_year | region | owner | budget_id | cost_center_code | account_key | cost_category | system_name | vendor_name | expense_item | project_id | asset_id | source_type | currency | m01 | m02 | m03 | m04 | m05 | m06 | m07 | m08 | m09 | m10 | m11 | m12 | note
2027 | JP | JP APP lead |  | JP-GDS-APP | JP¦5101 | SaaS / License | Salesforce | Salesforce | CRM licenses |  |  | MANUAL | JPY | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000
2027 | JP | JP APP lead |  | JP-GDS-APP | JP¦5103 | Outsourcing | SAP S/4HANA | NTT Data | ERP application maintenance |  |  | MANUAL | JPY | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000
2027 | JP | JP APP lead |  | JP-GDS-APP | JP¦5106 | Personnel | Common | Internal | Application team salaries |  |  | MANUAL | JPY | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000
2027 | JP | JP INF lead |  | JP-GDS-INF | JP¦5101 | Cloud | Azure | Microsoft | Azure commitment |  |  | MANUAL | JPY | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
2027 | JP | JP INF lead |  | JP-GDS-INF | JP¦5102 | Maintenance | Data center | Dell | Server maintenance |  |  | MANUAL | JPY | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000
2027 | JP | JP INF lead |  | JP-GDS-INF | JP¦5104 | Telecom | WAN | NTT Com | WAN circuits |  |  | MANUAL | JPY | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000
2027 | JP | JP INF lead |  | JP-GDS-INF | JP¦5105 | Depreciation | End-user devices | Lenovo | Laptop depreciation |  | FA-JP-0101 | MANUAL | JPY | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000
2027 | JP | JP INF lead |  | JP-GDS-INF | JP¦5106 | Personnel | Common | Internal | Infrastructure team salaries |  |  | MANUAL | JPY | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000
2027 | JP | JP DAT lead |  | JP-GDS-DAT | JP¦5101 | SaaS / License | Snowflake | Snowflake | Data platform |  |  | MANUAL | JPY | 2000000 | 2080000 | 2160000 | 2240000 | 2320000 | 2400000 | 2480000 | 2560000 | 2640000 | 2720000 | 2800000 | 2880000
2027 | JP | JP DAT lead |  | JP-GDS-DAT | JP¦5103 | Outsourcing | Data platform | Deloitte | Data engineering support | CAPEX-2027-011 |  | MANUAL | JPY | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000
2027 | JP | JP SEC lead |  | JP-GDS-SEC | JP¦5101 | SaaS / License | CrowdStrike | CrowdStrike | EDR licenses |  |  | MANUAL | JPY | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000
2027 | JP | JP SEC lead |  | JP-GDS-SEC | JP¦5103 | Outsourcing | SOC | IBM | Managed SOC |  |  | MANUAL | JPY | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000
2027 | JP | JP GOV lead |  | JP-GDS-GOV | JP¦5106 | Personnel | Common | Internal | Governance team salaries |  |  | MANUAL | JPY | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000
2027 | JP | JP GOV lead |  | JP-GDS-GOV | JP¦5107 | Travel & Training | Common | Various | Business travel |  |  | MANUAL | JPY | 480000 | 480000 | 480000 | 480000 | 480000 | 480000 | 1120000 | 1120000 | 1120000 | 1120000 | 1120000 | 1120000
2027 | JP | JP GOV lead |  | JP-GDS-GOV | JP¦5108 | Travel & Training | Common | Various | Training |  |  | MANUAL | JPY | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
2027 | NA | NA APP lead |  | NA-GDS-APP | NA¦6101 | SaaS / License | Salesforce | Salesforce | CRM licenses |  |  | MANUAL | USD | 22400 | 22400 | 22400 | 22400 | 22400 | 22400 | 22400 | 22400 | 22400 | 22400 | 22400 | 22400
2027 | NA | NA APP lead |  | NA-GDS-APP | NA¦6103 | Outsourcing | SAP S/4HANA | Accenture | ERP application maintenance |  |  | MANUAL | USD | 34667 | 34667 | 34667 | 34667 | 34667 | 34667 | 34667 | 34667 | 34667 | 34667 | 34667 | 34667
2027 | NA | NA APP lead |  | NA-GDS-APP | NA¦6106 | Personnel | Common | Internal | Application team salaries |  |  | MANUAL | USD | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000
2027 | NA | NA INF lead |  | NA-GDS-INF | NA¦6101 | Cloud | Azure | Microsoft | Azure commitment |  |  | MANUAL | USD | 26667 | 26667 | 26667 | 26667 | 26667 | 26667 | 26667 | 26667 | 26667 | 26667 | 26667 | 26667
2027 | NA | NA INF lead |  | NA-GDS-INF | NA¦6102 | Maintenance | Data center | Dell | Server maintenance |  |  | MANUAL | USD | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600
2027 | NA | NA INF lead |  | NA-GDS-INF | NA¦6104 | Telecom | WAN | AT&T | WAN circuits |  |  | MANUAL | USD | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800
2027 | NA | NA INF lead |  | NA-GDS-INF | NA¦6105 | Depreciation | End-user devices | Lenovo | Laptop depreciation |  | FA-NA-0101 | MANUAL | USD | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000
2027 | NA | NA INF lead |  | NA-GDS-INF | NA¦6106 | Personnel | Common | Internal | Infrastructure team salaries |  |  | MANUAL | USD | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
2027 | NA | NA DAT lead |  | NA-GDS-DAT | NA¦6101 | SaaS / License | Snowflake | Snowflake | Data platform |  |  | MANUAL | USD | 10667 | 11093 | 11520 | 11947 | 12373 | 12800 | 13227 | 13653 | 14080 | 14507 | 14933 | 15360
2027 | NA | NA DAT lead |  | NA-GDS-DAT | NA¦6103 | Outsourcing | Data platform | Deloitte | Data engineering support | CAPEX-2027-012 |  | MANUAL | USD | 17067 | 17067 | 17067 | 17067 | 17067 | 17067 | 17067 | 17067 | 17067 | 17067 | 17067 | 17067
2027 | NA | NA SEC lead |  | NA-GDS-SEC | NA¦6101 | SaaS / License | CrowdStrike | CrowdStrike | EDR licenses |  |  | MANUAL | USD | 13867 | 13867 | 13867 | 13867 | 13867 | 13867 | 13867 | 13867 | 13867 | 13867 | 13867 | 13867
2027 | NA | NA SEC lead |  | NA-GDS-SEC | NA¦6103 | Outsourcing | SOC | IBM | Managed SOC |  |  | MANUAL | USD | 18133 | 18133 | 18133 | 18133 | 18133 | 18133 | 18133 | 18133 | 18133 | 18133 | 18133 | 18133
2027 | NA | NA GOV lead |  | NA-GDS-GOV | NA¦6106 | Personnel | Common | Internal | Governance team salaries |  |  | MANUAL | USD | 21333 | 21333 | 21333 | 21333 | 21333 | 21333 | 21333 | 21333 | 21333 | 21333 | 21333 | 21333
2027 | NA | NA GOV lead |  | NA-GDS-GOV | NA¦6107 | Travel & Training | Common | Various | Business travel |  |  | MANUAL | USD | 2560 | 2560 | 2560 | 2560 | 2560 | 2560 | 5973 | 5973 | 5973 | 5973 | 5973 | 5973
2027 | NA | NA GOV lead |  | NA-GDS-GOV | NA¦6108 | Travel & Training | Common | Various | Training |  |  | MANUAL | USD | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600
2027 | EMEA | EMEA APP lead |  | EU-GDS-APP | EMEA¦7101 | SaaS / License | Salesforce | Salesforce | CRM licenses |  |  | MANUAL | GBP | 11053 | 11053 | 11053 | 11053 | 11053 | 11053 | 11053 | 11053 | 11053 | 11053 | 11053 | 11053
2027 | EMEA | EMEA APP lead |  | EU-GDS-APP | EMEA¦7103 | Outsourcing | SAP S/4HANA | Accenture | ERP application maintenance |  |  | MANUAL | GBP | 17105 | 17105 | 17105 | 17105 | 17105 | 17105 | 17105 | 17105 | 17105 | 17105 | 17105 | 17105
2027 | EMEA | EMEA APP lead |  | EU-GDS-APP | EMEA¦7106 | Personnel | Common | Internal | Application team salaries |  |  | MANUAL | GBP | 23684 | 23684 | 23684 | 23684 | 23684 | 23684 | 23684 | 23684 | 23684 | 23684 | 23684 | 23684
2027 | EMEA | EMEA INF lead |  | EU-GDS-INF | EMEA¦7101 | Cloud | Azure | Microsoft | Azure commitment |  |  | MANUAL | GBP | 13158 | 13158 | 13158 | 13158 | 13158 | 13158 | 13158 | 13158 | 13158 | 13158 | 13158 | 13158
2027 | EMEA | EMEA INF lead |  | EU-GDS-INF | EMEA¦7102 | Maintenance | Data center | Dell | Server maintenance |  |  | MANUAL | GBP | 4737 | 4737 | 4737 | 4737 | 4737 | 4737 | 4737 | 4737 | 4737 | 4737 | 4737 | 4737
2027 | EMEA | EMEA INF lead |  | EU-GDS-INF | EMEA¦7104 | Telecom | WAN | BT | WAN circuits |  |  | MANUAL | GBP | 6316 | 6316 | 6316 | 6316 | 6316 | 6316 | 6316 | 6316 | 6316 | 6316 | 6316 | 6316
2027 | EMEA | EMEA INF lead |  | EU-GDS-INF | EMEA¦7105 | Depreciation | End-user devices | Lenovo | Laptop depreciation |  | FA-EMEA-0101 | MANUAL | GBP | 7895 | 7895 | 7895 | 7895 | 7895 | 7895 | 7895 | 7895 | 7895 | 7895 | 7895 | 7895
2027 | EMEA | EMEA INF lead |  | EU-GDS-INF | EMEA¦7106 | Personnel | Common | Internal | Infrastructure team salaries |  |  | MANUAL | GBP | 19737 | 19737 | 19737 | 19737 | 19737 | 19737 | 19737 | 19737 | 19737 | 19737 | 19737 | 19737
2027 | EMEA | EMEA DAT lead |  | EU-GDS-DAT | EMEA¦7101 | SaaS / License | Snowflake | Snowflake | Data platform |  |  | MANUAL | GBP | 5263 | 5474 | 5684 | 5895 | 6105 | 6316 | 6526 | 6737 | 6947 | 7158 | 7368 | 7579
2027 | EMEA | EMEA DAT lead |  | EU-GDS-DAT | EMEA¦7103 | Outsourcing | Data platform | Deloitte | Data engineering support | CAPEX-2027-013 |  | MANUAL | GBP | 8421 | 8421 | 8421 | 8421 | 8421 | 8421 | 8421 | 8421 | 8421 | 8421 | 8421 | 8421
2027 | EMEA | EMEA SEC lead |  | EU-GDS-SEC | EMEA¦7101 | SaaS / License | CrowdStrike | CrowdStrike | EDR licenses |  |  | MANUAL | GBP | 6842 | 6842 | 6842 | 6842 | 6842 | 6842 | 6842 | 6842 | 6842 | 6842 | 6842 | 6842
2027 | EMEA | EMEA SEC lead |  | EU-GDS-SEC | EMEA¦7103 | Outsourcing | SOC | IBM | Managed SOC |  |  | MANUAL | GBP | 8947 | 8947 | 8947 | 8947 | 8947 | 8947 | 8947 | 8947 | 8947 | 8947 | 8947 | 8947
2027 | EMEA | EMEA GOV lead |  | EU-GDS-GOV | EMEA¦7106 | Personnel | Common | Internal | Governance team salaries |  |  | MANUAL | GBP | 10526 | 10526 | 10526 | 10526 | 10526 | 10526 | 10526 | 10526 | 10526 | 10526 | 10526 | 10526
2027 | EMEA | EMEA GOV lead |  | EU-GDS-GOV | EMEA¦7107 | Travel & Training | Common | Various | Business travel |  |  | MANUAL | GBP | 1263 | 1263 | 1263 | 1263 | 1263 | 1263 | 2947 | 2947 | 2947 | 2947 | 2947 | 2947
2027 | EMEA | EMEA GOV lead |  | EU-GDS-GOV | EMEA¦7108 | Travel & Training | Common | Various | Training |  |  | MANUAL | GBP | 2368 | 2368 | 2368 | 2368 | 2368 | 2368 | 789 | 789 | 789 | 789 | 789 | 789
2027 | JP | JP APP lead | M365-FY27 | JP-GDS-APP | JP¦5101 | SaaS / License | Microsoft 365 | Microsoft | M365 E5 (prepaid, amortized) |  |  | MANUAL | JPY | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000
2027 | EMEA | EMEA DAT lead |  | EU-GDS-DAT | EMEA¦7101 | SaaS / License | Tableau | Salesforce | Tableau licenses (USD) |  |  | MANUAL | USD | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000
2027 | JP | Sales BP | BT-0012 | JP-SLS-100 | JP¦5101 | SaaS / License | Sales CRM add-on | HubSpot | Marketing automation |  |  | MANUAL | JPY | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
2027 | JP | R&D BP | BT-0031 | JP-RND-200 | JP¦5102 | Maintenance | ELN | Benchling | Electronic lab notebook support |  |  | MANUAL | JPY | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000

## Actuals
region | fiscal_year | month | cost_center_code | local_account_code | currency | amount | description | import_batch
EMEA | 2027 | 1 | EU-GDS-APP | 7101 | GBP | 10528 |  | 202701
EMEA | 2027 | 1 | EU-GDS-APP | 7103 | GBP | 17692 |  | 202701
EMEA | 2027 | 1 | EU-GDS-APP | 7106 | GBP | 22919 |  | 202701
EMEA | 2027 | 1 | EU-GDS-DAT | 7101 | GBP | 12601 |  | 202701
EMEA | 2027 | 1 | EU-GDS-DAT | 7103 | GBP | 1684 |  | 202701
EMEA | 2027 | 1 | EU-GDS-GOV | 7106 | GBP | 10496 |  | 202701
EMEA | 2027 | 1 | EU-GDS-GOV | 7107 | GBP | 1219 |  | 202701
EMEA | 2027 | 1 | EU-GDS-GOV | 7108 | GBP | 2368 |  | 202701
EMEA | 2027 | 1 | EU-GDS-INF | 7101 | GBP | 13273 |  | 202701
EMEA | 2027 | 1 | EU-GDS-INF | 7102 | GBP | 4820 |  | 202701
EMEA | 2027 | 1 | EU-GDS-INF | 7104 | GBP | 6553 |  | 202701
EMEA | 2027 | 1 | EU-GDS-INF | 7105 | GBP | 7591 |  | 202701
EMEA | 2027 | 1 | EU-GDS-INF | 7106 | GBP | 20491 |  | 202701
EMEA | 2027 | 1 | EU-GDS-SEC | 7101 | GBP | 6660 |  | 202701
EMEA | 2027 | 1 | EU-GDS-SEC | 7103 | GBP | 8969 |  | 202701
JP | 2027 | 1 | JP-GDS-APP | 5101 | JPY | 16346451 |  | 202701
JP | 2027 | 1 | JP-GDS-APP | 5103 | JPY | 6208929 |  | 202701
JP | 2027 | 1 | JP-GDS-APP | 5106 | JPY | 8893861 |  | 202701
JP | 2027 | 1 | JP-GDS-DAT | 5101 | JPY | 2031300 |  | 202701
JP | 2027 | 1 | JP-GDS-DAT | 5103 | JPY | 3083772 |  | 202701
JP | 2027 | 1 | JP-GDS-GOV | 5106 | JPY | 4032966 |  | 202701
JP | 2027 | 1 | JP-GDS-GOV | 5107 | JPY | 456975 |  | 202701
JP | 2027 | 1 | JP-GDS-GOV | 5108 | JPY | 865477 |  | 202701
JP | 2027 | 1 | JP-GDS-INF | 5101 | JPY | 5009696 |  | 202701
JP | 2027 | 1 | JP-GDS-INF | 5102 | JPY | 1733369 |  | 202701
JP | 2027 | 1 | JP-GDS-INF | 5104 | JPY | 2418005 |  | 202701
JP | 2027 | 1 | JP-GDS-INF | 5105 | JPY | 3033708 |  | 202701
JP | 2027 | 1 | JP-GDS-INF | 5106 | JPY | 7661206 |  | 202701
JP | 2027 | 1 | JP-GDS-SEC | 5101 | JPY | 2674862 |  | 202701
JP | 2027 | 1 | JP-GDS-SEC | 5103 | JPY | 3487030 |  | 202701
JP | 2027 | 1 | JP-RND-200 | 5102 | JPY | 2200784 |  | 202701
JP | 2027 | 1 | JP-SLS-100 | 5101 | JPY | 1489535 |  | 202701
NA | 2027 | 1 | NA-GDS-APP | 6101 | USD | 22388 |  | 202701
NA | 2027 | 1 | NA-GDS-APP | 6103 | USD | 34053 |  | 202701
NA | 2027 | 1 | NA-GDS-APP | 6106 | USD | 46608 |  | 202701
NA | 2027 | 1 | NA-GDS-DAT | 6101 | USD | 10376 |  | 202701
NA | 2027 | 1 | NA-GDS-DAT | 6103 | USD | 16929 |  | 202701
NA | 2027 | 1 | NA-GDS-GOV | 6106 | USD | 20768 |  | 202701
NA | 2027 | 1 | NA-GDS-GOV | 6107 | USD | 2508 |  | 202701
NA | 2027 | 1 | NA-GDS-GOV | 6108 | USD | 4914 |  | 202701
NA | 2027 | 1 | NA-GDS-INF | 6101 | USD | 26220 |  | 202701
NA | 2027 | 1 | NA-GDS-INF | 6102 | USD | 9704 |  | 202701
NA | 2027 | 1 | NA-GDS-INF | 6104 | USD | 12612 |  | 202701
NA | 2027 | 1 | NA-GDS-INF | 6105 | USD | 15501 |  | 202701
NA | 2027 | 1 | NA-GDS-INF | 6106 | USD | 38365 |  | 202701
NA | 2027 | 1 | NA-GDS-SEC | 6101 | USD | 14208 |  | 202701
NA | 2027 | 1 | NA-GDS-SEC | 6103 | USD | 18113 |  | 202701
EMEA | 2027 | 2 | EU-GDS-APP | 7101 | GBP | 10778 |  | 202702
EMEA | 2027 | 2 | EU-GDS-APP | 7103 | GBP | 17771 |  | 202702
EMEA | 2027 | 2 | EU-GDS-APP | 7106 | GBP | 22935 |  | 202702
EMEA | 2027 | 2 | EU-GDS-DAT | 7101 | GBP | 12594 |  | 202702
EMEA | 2027 | 2 | EU-GDS-DAT | 7103 | GBP | 1684 |  | 202702
EMEA | 2027 | 2 | EU-GDS-GOV | 7106 | GBP | 10017 |  | 202702
EMEA | 2027 | 2 | EU-GDS-GOV | 7107 | GBP | 1254 |  | 202702
EMEA | 2027 | 2 | EU-GDS-GOV | 7108 | GBP | 2417 |  | 202702
EMEA | 2027 | 2 | EU-GDS-INF | 7101 | GBP | 13447 |  | 202702
EMEA | 2027 | 2 | EU-GDS-INF | 7102 | GBP | 4704 |  | 202702
EMEA | 2027 | 2 | EU-GDS-INF | 7104 | GBP | 6225 |  | 202702
EMEA | 2027 | 2 | EU-GDS-INF | 7105 | GBP | 7608 |  | 202702
EMEA | 2027 | 2 | EU-GDS-INF | 7106 | GBP | 19918 |  | 202702
EMEA | 2027 | 2 | EU-GDS-SEC | 7101 | GBP | 6758 |  | 202702
EMEA | 2027 | 2 | EU-GDS-SEC | 7103 | GBP | 9228 |  | 202702
JP | 2027 | 2 | JP-GDS-APP | 5101 | JPY | 15995352 |  | 202702
JP | 2027 | 2 | JP-GDS-APP | 5103 | JPY | 6471850 |  | 202702
JP | 2027 | 2 | JP-GDS-APP | 5106 | JPY | 9219750 |  | 202702
JP | 2027 | 2 | JP-GDS-DAT | 5101 | JPY | 2029902 |  | 202702
JP | 2027 | 2 | JP-GDS-DAT | 5103 | JPY | 3180821 |  | 202702
JP | 2027 | 2 | JP-GDS-GOV | 5106 | JPY | 4157515 |  | 202702
JP | 2027 | 2 | JP-GDS-GOV | 5107 | JPY | 144000 |  | 202702
JP | 2027 | 2 | JP-GDS-GOV | 5108 | JPY | 875057 |  | 202702
JP | 2027 | 2 | JP-GDS-INF | 5101 | JPY | 4928506 |  | 202702
JP | 2027 | 2 | JP-GDS-INF | 5102 | JPY | 1729082 |  | 202702
JP | 2027 | 2 | JP-GDS-INF | 5104 | JPY | 2360438 |  | 202702
JP | 2027 | 2 | JP-GDS-INF | 5105 | JPY | 2965450 |  | 202702
JP | 2027 | 2 | JP-GDS-INF | 5106 | JPY | 7596821 |  | 202702
JP | 2027 | 2 | JP-GDS-SEC | 5101 | JPY | 2543417 |  | 202702
JP | 2027 | 2 | JP-GDS-SEC | 5103 | JPY | 3519072 |  | 202702
JP | 2027 | 2 | JP-RND-200 | 5102 | JPY | 2276767 |  | 202702
JP | 2027 | 2 | JP-SLS-100 | 5101 | JPY | 1552103 |  | 202702
NA | 2027 | 2 | NA-GDS-APP | 6101 | USD | 23061 |  | 202702
NA | 2027 | 2 | NA-GDS-APP | 6103 | USD | 35692 |  | 202702
NA | 2027 | 2 | NA-GDS-APP | 6106 | USD | 47695 |  | 202702
NA | 2027 | 2 | NA-GDS-DAT | 6101 | USD | 10885 |  | 202702
NA | 2027 | 2 | NA-GDS-DAT | 6103 | USD | 16957 |  | 202702
NA | 2027 | 2 | NA-GDS-GOV | 6106 | USD | 20970 |  | 202702
NA | 2027 | 2 | NA-GDS-GOV | 6107 | USD | 2483 |  | 202702
NA | 2027 | 2 | NA-GDS-GOV | 6108 | USD | 4880 |  | 202702
NA | 2027 | 2 | NA-GDS-INF | 6101 | USD | 26693 |  | 202702
NA | 2027 | 2 | NA-GDS-INF | 6102 | USD | 9167 |  | 202702
NA | 2027 | 2 | NA-GDS-INF | 6104 | USD | 12620 |  | 202702
NA | 2027 | 2 | NA-GDS-INF | 6105 | USD | 15434 |  | 202702
NA | 2027 | 2 | NA-GDS-INF | 6106 | USD | 39309 |  | 202702
NA | 2027 | 2 | NA-GDS-SEC | 6101 | USD | 13375 |  | 202702
NA | 2027 | 2 | NA-GDS-SEC | 6103 | USD | 17270 |  | 202702
EMEA | 2027 | 3 | EU-GDS-APP | 7101 | GBP | 10758 |  | 202703
EMEA | 2027 | 3 | EU-GDS-APP | 7103 | GBP | 17720 |  | 202703
EMEA | 2027 | 3 | EU-GDS-APP | 7106 | GBP | 23830 |  | 202703
EMEA | 2027 | 3 | EU-GDS-DAT | 7101 | GBP | 12747 |  | 202703
EMEA | 2027 | 3 | EU-GDS-DAT | 7103 | GBP | 2526 |  | 202703
EMEA | 2027 | 3 | EU-GDS-GOV | 7106 | GBP | 10417 |  | 202703
EMEA | 2027 | 3 | EU-GDS-GOV | 7107 | GBP | 1282 |  | 202703
EMEA | 2027 | 3 | EU-GDS-GOV | 7108 | GBP | 2272 |  | 202703
EMEA | 2027 | 3 | EU-GDS-INF | 7101 | GBP | 12600 |  | 202703
EMEA | 2027 | 3 | EU-GDS-INF | 7102 | GBP | 4576 |  | 202703
EMEA | 2027 | 3 | EU-GDS-INF | 7104 | GBP | 6228 |  | 202703
EMEA | 2027 | 3 | EU-GDS-INF | 7105 | GBP | 8143 |  | 202703
EMEA | 2027 | 3 | EU-GDS-INF | 7106 | GBP | 19373 |  | 202703
EMEA | 2027 | 3 | EU-GDS-SEC | 7101 | GBP | 6581 |  | 202703
EMEA | 2027 | 3 | EU-GDS-SEC | 7103 | GBP | 8838 |  | 202703
JP | 2027 | 3 | JP-GDS-APP | 5101 | JPY | 16242721 |  | 202703
JP | 2027 | 3 | JP-GDS-APP | 5103 | JPY | 6196935 |  | 202703
JP | 2027 | 3 | JP-GDS-APP | 5106 | JPY | 8650280 |  | 202703
JP | 2027 | 3 | JP-GDS-DAT | 5101 | JPY | 2242546 |  | 202703
JP | 2027 | 3 | JP-GDS-DAT | 5103 | JPY | 3051292 |  | 202703
JP | 2027 | 3 | JP-GDS-GOV | 5106 | JPY | 4095893 |  | 202703
JP | 2027 | 3 | JP-GDS-GOV | 5107 | JPY | 192000 |  | 202703
JP | 2027 | 3 | JP-GDS-GOV | 5108 | JPY | 886667 |  | 202703
JP | 2027 | 3 | JP-GDS-INF | 5101 | JPY | 5189315 |  | 202703
JP | 2027 | 3 | JP-GDS-INF | 5102 | JPY | 1759974 |  | 202703
JP | 2027 | 3 | JP-GDS-INF | 5104 | JPY | 2398313 |  | 202703
JP | 2027 | 3 | JP-GDS-INF | 5105 | JPY | 2934820 |  | 202703
JP | 2027 | 3 | JP-GDS-INF | 5106 | JPY | 7289765 |  | 202703
JP | 2027 | 3 | JP-GDS-SEC | 5101 | JPY | 2632699 |  | 202703
JP | 2027 | 3 | JP-GDS-SEC | 5103 | JPY | 3375074 |  | 202703
JP | 2027 | 3 | JP-RND-200 | 5102 | JPY | 2256320 |  | 202703
JP | 2027 | 3 | JP-SLS-100 | 5101 | JPY | 1519394 |  | 202703
NA | 2027 | 3 | NA-GDS-APP | 6101 | USD | 62720 |  | 202703
NA | 2027 | 3 | NA-GDS-APP | 6103 | USD | 35922 |  | 202703
NA | 2027 | 3 | NA-GDS-APP | 6106 | USD | 48145 |  | 202703
NA | 2027 | 3 | NA-GDS-DAT | 6101 | USD | 11322 |  | 202703
NA | 2027 | 3 | NA-GDS-DAT | 6103 | USD | 16346 |  | 202703
NA | 2027 | 3 | NA-GDS-GOV | 6106 | USD | 20587 |  | 202703
NA | 2027 | 3 | NA-GDS-GOV | 6107 | USD | 2619 |  | 202703
NA | 2027 | 3 | NA-GDS-GOV | 6108 | USD | 4658 |  | 202703
NA | 2027 | 3 | NA-GDS-INF | 6101 | USD | 27621 |  | 202703
NA | 2027 | 3 | NA-GDS-INF | 6102 | USD | 9897 |  | 202703
NA | 2027 | 3 | NA-GDS-INF | 6104 | USD | 12279 |  | 202703
NA | 2027 | 3 | NA-GDS-INF | 6105 | USD | 15690 |  | 202703
NA | 2027 | 3 | NA-GDS-INF | 6106 | USD | 38092 |  | 202703
NA | 2027 | 3 | NA-GDS-SEC | 6101 | USD | 13202 |  | 202703
NA | 2027 | 3 | NA-GDS-SEC | 6103 | USD | 18088 |  | 202703
EMEA | 2027 | 4 | EU-GDS-APP | 7101 | GBP | 11189 |  | 202704
EMEA | 2027 | 4 | EU-GDS-APP | 7103 | GBP | 16811 |  | 202704
EMEA | 2027 | 4 | EU-GDS-APP | 7106 | GBP | 24419 |  | 202704
EMEA | 2027 | 4 | EU-GDS-DAT | 7101 | GBP | 13289 |  | 202704
EMEA | 2027 | 4 | EU-GDS-DAT | 7103 | GBP | 3368 |  | 202704
EMEA | 2027 | 4 | EU-GDS-GOV | 7106 | GBP | 10173 |  | 202704
EMEA | 2027 | 4 | EU-GDS-GOV | 7107 | GBP | 1263 |  | 202704
EMEA | 2027 | 4 | EU-GDS-GOV | 7108 | GBP | 2369 |  | 202704
EMEA | 2027 | 4 | EU-GDS-INF | 7101 | GBP | 13282 |  | 202704
EMEA | 2027 | 4 | EU-GDS-INF | 7102 | GBP | 4837 |  | 202704
EMEA | 2027 | 4 | EU-GDS-INF | 7104 | GBP | 6538 |  | 202704
EMEA | 2027 | 4 | EU-GDS-INF | 7105 | GBP | 8073 |  | 202704
EMEA | 2027 | 4 | EU-GDS-INF | 7106 | GBP | 19725 |  | 202704
EMEA | 2027 | 4 | EU-GDS-SEC | 7101 | GBP | 7060 |  | 202704
EMEA | 2027 | 4 | EU-GDS-SEC | 7103 | GBP | 9239 |  | 202704
JP | 2027 | 4 | JP-GDS-APP | 5101 | JPY | 16238174 |  | 202704
JP | 2027 | 4 | JP-GDS-APP | 5103 | JPY | 6428683 |  | 202704
JP | 2027 | 4 | JP-GDS-APP | 5106 | JPY | 8730824 |  | 202704
JP | 2027 | 4 | JP-GDS-DAT | 5101 | JPY | 2151802 |  | 202704
JP | 2027 | 4 | JP-GDS-DAT | 5103 | JPY | 3232446 |  | 202704
JP | 2027 | 4 | JP-GDS-GOV | 5106 | JPY | 3902454 |  | 202704
JP | 2027 | 4 | JP-GDS-GOV | 5107 | JPY | 461059 |  | 202704
JP | 2027 | 4 | JP-GDS-GOV | 5108 | JPY | 925585 |  | 202704
JP | 2027 | 4 | JP-GDS-INF | 5101 | JPY | 6000000 |  | 202704
JP | 2027 | 4 | JP-GDS-INF | 5102 | JPY | 1842212 |  | 202704
JP | 2027 | 4 | JP-GDS-INF | 5104 | JPY | 2293562 |  | 202704
JP | 2027 | 4 | JP-GDS-INF | 5105 | JPY | 3008102 |  | 202704
JP | 2027 | 4 | JP-GDS-INF | 5106 | JPY | 7512736 |  | 202704
JP | 2027 | 4 | JP-GDS-SEC | 5101 | JPY | 2609083 |  | 202704
JP | 2027 | 4 | JP-GDS-SEC | 5103 | JPY | 5233231 |  | 202704
JP | 2027 | 4 | JP-RND-200 | 5102 | JPY | 2117153 |  | 202704
JP | 2027 | 4 | JP-SLS-100 | 5101 | JPY | 1543332 |  | 202704
NA | 2027 | 4 | NA-GDS-APP | 6101 | USD | 23022 |  | 202704
NA | 2027 | 4 | NA-GDS-APP | 6103 | USD | 33405 |  | 202704
NA | 2027 | 4 | NA-GDS-APP | 6106 | USD | 46735 |  | 202704
NA | 2027 | 4 | NA-GDS-DAT | 6101 | USD | 11482 |  | 202704
NA | 2027 | 4 | NA-GDS-DAT | 6103 | USD | 16371 |  | 202704
NA | 2027 | 4 | NA-GDS-GOV | 6106 | USD | 21748 |  | 202704
NA | 2027 | 4 | NA-GDS-GOV | 6107 | USD | 2659 |  | 202704
NA | 2027 | 4 | NA-GDS-GOV | 6108 | USD | 4784 |  | 202704
NA | 2027 | 4 | NA-GDS-INF | 6101 | USD | 26991 |  | 202704
NA | 2027 | 4 | NA-GDS-INF | 6102 | USD | 9794 |  | 202704
NA | 2027 | 4 | NA-GDS-INF | 6104 | USD | 12891 |  | 202704
NA | 2027 | 4 | NA-GDS-INF | 6105 | USD | 15276 |  | 202704
NA | 2027 | 4 | NA-GDS-INF | 6106 | USD | 41148 |  | 202704
NA | 2027 | 4 | NA-GDS-SEC | 6101 | USD | 14361 |  | 202704
NA | 2027 | 4 | NA-GDS-SEC | 6103 | USD | 18823 |  | 202704
EMEA | 2027 | 5 | EU-GDS-APP | 7101 | GBP | 11452 |  | 202705
EMEA | 2027 | 5 | EU-GDS-APP | 7103 | GBP | 16589 |  | 202705
EMEA | 2027 | 5 | EU-GDS-APP | 7106 | GBP | 24291 |  | 202705
EMEA | 2027 | 5 | EU-GDS-DAT | 7101 | GBP | 13077 |  | 202705
EMEA | 2027 | 5 | EU-GDS-DAT | 7103 | GBP | 4210 |  | 202705
EMEA | 2027 | 5 | EU-GDS-GOV | 7106 | GBP | 10003 |  | 202705
EMEA | 2027 | 5 | EU-GDS-GOV | 7107 | GBP | 1237 |  | 202705
EMEA | 2027 | 5 | EU-GDS-GOV | 7108 | GBP | 2303 |  | 202705
EMEA | 2027 | 5 | EU-GDS-INF | 7101 | GBP | 13577 |  | 202705
EMEA | 2027 | 5 | EU-GDS-INF | 7102 | GBP | 4642 |  | 202705
EMEA | 2027 | 5 | EU-GDS-INF | 7104 | GBP | 6412 |  | 202705
EMEA | 2027 | 5 | EU-GDS-INF | 7105 | GBP | 7604 |  | 202705
EMEA | 2027 | 5 | EU-GDS-INF | 7106 | GBP | 18983 |  | 202705
EMEA | 2027 | 5 | EU-GDS-SEC | 7101 | GBP | 6718 |  | 202705
EMEA | 2027 | 5 | EU-GDS-SEC | 7103 | GBP | 8904 |  | 202705
JP | 2027 | 5 | JP-GDS-APP | 5101 | JPY | 16578050 |  | 202705
JP | 2027 | 5 | JP-GDS-APP | 5103 | JPY | 8775000 |  | 202705
JP | 2027 | 5 | JP-GDS-APP | 5106 | JPY | 9058221 |  | 202705
JP | 2027 | 5 | JP-GDS-DAT | 5101 | JPY | 2291304 |  | 202705
JP | 2027 | 5 | JP-GDS-DAT | 5103 | JPY | 3260196 |  | 202705
JP | 2027 | 5 | JP-GDS-GOV | 5106 | JPY | 3938885 |  | 202705
JP | 2027 | 5 | JP-GDS-GOV | 5107 | JPY | 458547 |  | 202705
JP | 2027 | 5 | JP-GDS-GOV | 5108 | JPY | 861527 |  | 202705
JP | 2027 | 5 | JP-GDS-INF | 5101 | JPY | 6250000 |  | 202705
JP | 2027 | 5 | JP-GDS-INF | 5102 | JPY | 1739278 |  | 202705
JP | 2027 | 5 | JP-GDS-INF | 5104 | JPY | 2292874 |  | 202705
JP | 2027 | 5 | JP-GDS-INF | 5105 | JPY | 2972360 |  | 202705
JP | 2027 | 5 | JP-GDS-INF | 5106 | JPY | 7479508 |  | 202705
JP | 2027 | 5 | JP-GDS-SEC | 5101 | JPY | 2605695 |  | 202705
JP | 2027 | 5 | JP-GDS-SEC | 5103 | JPY | 5048565 |  | 202705
JP | 2027 | 5 | JP-RND-200 | 5102 | JPY | 2114081 |  | 202705
JP | 2027 | 5 | JP-SLS-100 | 5101 | JPY | 1552194 |  | 202705
NA | 2027 | 5 | NA-GDS-APP | 6101 | USD | 21841 |  | 202705
NA | 2027 | 5 | NA-GDS-APP | 6103 | USD | 33483 |  | 202705
NA | 2027 | 5 | NA-GDS-APP | 6106 | USD | 45618 |  | 202705
NA | 2027 | 5 | NA-GDS-DAT | 6101 | USD | 12700 |  | 202705
NA | 2027 | 5 | NA-GDS-DAT | 6103 | USD | 16740 |  | 202705
NA | 2027 | 5 | NA-GDS-GOV | 6106 | USD | 21289 |  | 202705
NA | 2027 | 5 | NA-GDS-GOV | 6107 | USD | 2628 |  | 202705
NA | 2027 | 5 | NA-GDS-GOV | 6108 | USD | 4714 |  | 202705
NA | 2027 | 5 | NA-GDS-INF | 6101 | USD | 26571 |  | 202705
NA | 2027 | 5 | NA-GDS-INF | 6102 | USD | 9876 |  | 202705
NA | 2027 | 5 | NA-GDS-INF | 6104 | USD | 12232 |  | 202705
NA | 2027 | 5 | NA-GDS-INF | 6105 | USD | 15200 |  | 202705
NA | 2027 | 5 | NA-GDS-INF | 6106 | USD | 40211 |  | 202705
NA | 2027 | 5 | NA-GDS-SEC | 6101 | USD | 13833 |  | 202705
NA | 2027 | 5 | NA-GDS-SEC | 6103 | USD | 18635 |  | 202705
EMEA | 2027 | 6 | EU-GDS-APP | 7101 | GBP | 10945 |  | 202706
EMEA | 2027 | 6 | EU-GDS-APP | 7103 | GBP | 16599 |  | 202706
EMEA | 2027 | 6 | EU-GDS-APP | 7106 | GBP | 23522 |  | 202706
EMEA | 2027 | 6 | EU-GDS-DAT | 7101 | GBP | 13587 |  | 202706
EMEA | 2027 | 6 | EU-GDS-DAT | 7103 | GBP | 5053 |  | 202706
EMEA | 2027 | 6 | EU-GDS-GOV | 7106 | GBP | 10757 |  | 202706
EMEA | 2027 | 6 | EU-GDS-GOV | 7107 | GBP | 1259 |  | 202706
EMEA | 2027 | 6 | EU-GDS-GOV | 7108 | GBP | 2309 |  | 202706
EMEA | 2027 | 6 | EU-GDS-INF | 7101 | GBP | 13427 |  | 202706
EMEA | 2027 | 6 | EU-GDS-INF | 7102 | GBP | 4842 |  | 202706
EMEA | 2027 | 6 | EU-GDS-INF | 7104 | GBP | 6097 |  | 202706
EMEA | 2027 | 6 | EU-GDS-INF | 7105 | GBP | 8088 |  | 202706
EMEA | 2027 | 6 | EU-GDS-INF | 7106 | GBP | 18775 |  | 202706
EMEA | 2027 | 6 | EU-GDS-SEC | 7101 | GBP | 6782 |  | 202706
EMEA | 2027 | 6 | EU-GDS-SEC | 7103 | GBP | 8928 |  | 202706
JP | 2027 | 6 | JP-GDS-APP | 5101 | JPY | 16006939 |  | 202706
JP | 2027 | 6 | JP-GDS-APP | 5103 | JPY | 9100000 |  | 202706
JP | 2027 | 6 | JP-GDS-APP | 5106 | JPY | 9317644 |  | 202706
JP | 2027 | 6 | JP-GDS-DAT | 5101 | JPY | 2443542 |  | 202706
JP | 2027 | 6 | JP-GDS-DAT | 5103 | JPY | 3205031 |  | 202706
JP | 2027 | 6 | JP-GDS-GOV | 5106 | JPY | 4040715 |  | 202706
JP | 2027 | 6 | JP-GDS-GOV | 5107 | JPY | 489188 |  | 202706
JP | 2027 | 6 | JP-GDS-GOV | 5108 | JPY | 891384 |  | 202706
JP | 2027 | 6 | JP-GDS-INF | 5101 | JPY | 6500000 |  | 202706
JP | 2027 | 6 | JP-GDS-INF | 5102 | JPY | 1804219 |  | 202706
JP | 2027 | 6 | JP-GDS-INF | 5104 | JPY | 2324487 |  | 202706
JP | 2027 | 6 | JP-GDS-INF | 5105 | JPY | 2930937 |  | 202706
JP | 2027 | 6 | JP-GDS-INF | 5106 | JPY | 7715718 |  | 202706
JP | 2027 | 6 | JP-GDS-SEC | 5101 | JPY | 2576752 |  | 202706
JP | 2027 | 6 | JP-GDS-SEC | 5103 | JPY | 5244657 |  | 202706
JP | 2027 | 6 | JP-RND-200 | 5102 | JPY | 2177539 |  | 202706
JP | 2027 | 6 | JP-SLS-100 | 5101 | JPY | 1460045 |  | 202706
NA | 2027 | 6 | NA-GDS-APP | 6101 | USD | 22117 |  | 202706
NA | 2027 | 6 | NA-GDS-APP | 6103 | USD | 33657 |  | 202706
NA | 2027 | 6 | NA-GDS-APP | 6106 | USD | 47410 |  | 202706
NA | 2027 | 6 | NA-GDS-DAT | 6101 | USD | 13304 |  | 202706
NA | 2027 | 6 | NA-GDS-DAT | 6103 | USD | 16620 |  | 202706
NA | 2027 | 6 | NA-GDS-GOV | 6106 | USD | 21762 |  | 202706
NA | 2027 | 6 | NA-GDS-GOV | 6107 | USD | 2618 |  | 202706
NA | 2027 | 6 | NA-GDS-GOV | 6108 | USD | 4573 |  | 202706
NA | 2027 | 6 | NA-GDS-INF | 6101 | USD | 26816 |  | 202706
NA | 2027 | 6 | NA-GDS-INF | 6102 | USD | 9809 |  | 202706
NA | 2027 | 6 | NA-GDS-INF | 6104 | USD | 12238 |  | 202706
NA | 2027 | 6 | NA-GDS-INF | 6105 | USD | 15418 |  | 202706
NA | 2027 | 6 | NA-GDS-INF | 6106 | USD | 38535 |  | 202706
NA | 2027 | 6 | NA-GDS-SEC | 6101 | USD | 13357 |  | 202706
NA | 2027 | 6 | NA-GDS-SEC | 6103 | USD | 18363 |  | 202706

## Prior_Forecast
cost_center_code | account_key | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YTD | MTG | FY | as_of_close_month | Setup (IT Finance, once, Excel desktop) / 初回設定（ITファイナンス、1回だけ、デスクトップ版Excel）
JP-GDS-APP | JP¦5101 | 16346451 | 15995352 | 16242721 | 16238174 | 16578050 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 81400748 | 113400000 | 194800748 | 5 | 1. Delete the placeholder table on the left. / 左の仮テーブルを削除する。
JP-GDS-APP | JP¦5103 | 6208929 | 6471850 | 6196935 | 6428683 | 8775000 | 7475000 | 7475000 | 7475000 | 7475000 | 7475000 | 7475000 | 7475000 | 34081397 | 52325000 | 86406397 | 5 | 2. Data > Get Data > From Other Sources > Blank Query. Paste the M code below and name the query Prior_Forecast. / 空のクエリに下のMコードを貼り、クエリ名をPrior_Forecastにする。
JP-GDS-APP | JP¦5106 | 8893861 | 9219750 | 8650280 | 8730824 | 9058221 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 44552936 | 63000000 | 107552936 | 5 | 3. Close & Load To > Existing worksheet > Prior_Forecast!$A$1. / 「閉じて次に読み込む」でこのシートのA1に読み込む。
JP-GDS-DAT | JP¦5101 | 2031300 | 2029902 | 2242546 | 2151802 | 2291304 | 2400000 | 2480000 | 2560000 | 2640000 | 2720000 | 2800000 | 2880000 | 10746854 | 18480000 | 29226854 | 5 | 4. Data > Queries & Connections > Prior_Forecast > Properties: uncheck 'Refresh this connection on Refresh All'. / 接続のプロパティで「すべて更新でこの接続を更新する」をオフにする。
JP-GDS-DAT | JP¦5103 | 3083772 | 3180821 | 3051292 | 3232446 | 3260196 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 15808527 | 22400000 | 38208527 | 5 | let
JP-GDS-GOV | JP¦5106 | 4032966 | 4157515 | 4095893 | 3902454 | 3938885 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 20127713 | 28000000 | 48127713 | 5 | Src = Excel.CurrentWorkbook(){[Name="rng_BvA"]}[Content],
JP-GDS-GOV | JP¦5107 | 456975 | 144000 | 192000 | 461059 | 458547 | 480000 | 1120000 | 1120000 | 1120000 | 1120000 | 1120000 | 1120000 | 1712581 | 7200000 | 8912581 | 5 | Hdr = Table.PromoteHeaders(Src, [PromoteAllScalars=true]),
JP-GDS-GOV | JP¦5108 | 865477 | 875057 | 886667 | 925585 | 861527 | 900000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 4414313 | 2700000 | 7114313 | 5 | Rows = Table.SelectRows(Hdr, each [line] = "Actual + Forecast" and [cost_center_code] <> null and [cost_center_code] <> ""),
JP-GDS-INF | JP¦5101 | 5009696 | 4928506 | 5189315 | 6000000 | 6250000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 27377517 | 35000000 | 62377517 | 5 | Keep = Table.SelectColumns(Rows, {"cost_center_code","account_key","Jan","Feb","Mar","Apr","May","Jun","Jul","Aug","Sep","Oct","Nov","Dec","YTD","MTG","FY"}),
JP-GDS-INF | JP¦5102 | 1733369 | 1729082 | 1759974 | 1842212 | 1739278 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 8803915 | 12600000 | 21403915 | 5 | Close = Excel.CurrentWorkbook(){[Name="prm_close_month"]}[Content]{0}[Column1],
JP-GDS-INF | JP¦5104 | 2418005 | 2360438 | 2398313 | 2293562 | 2292874 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 11763192 | 16800000 | 28563192 | 5 | Result = Table.AddColumn(Keep, "as_of_close_month", each Close, Int64.Type)
JP-GDS-INF | JP¦5105 | 3033708 | 2965450 | 2934820 | 3008102 | 2972360 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 14914440 | 21000000 | 35914440 | 5 | in
JP-GDS-INF | JP¦5106 | 7661206 | 7596821 | 7289765 | 7512736 | 7479508 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 37540036 | 52500000 | 90040036 | 5 | Result
JP-GDS-SEC | JP¦5101 | 2674862 | 2543417 | 2632699 | 2609083 | 2605695 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 13065756 | 18200000 | 31265756 | 5
JP-GDS-SEC | JP¦5103 | 3487030 | 3519072 | 3375074 | 5233231 | 5048565 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 20662972 | 23800000 | 44462972 | 5
JP-RND-200 | JP¦5102 | 2200784 | 2276767 | 2256320 | 2117153 | 2114081 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 10965105 | 15400000 | 26365105 | 5
JP-SLS-100 | JP¦5101 | 1489535 | 1552103 | 1519394 | 1543332 | 1552194 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 7656558 | 10500000 | 18156558 | 5
NA-GDS-APP | NA¦6101 | 3358200 | 3459150 | 9408000 | 3453300 | 3276150 | 3360000 | 3360000 | 3360000 | 3360000 | 3360000 | 3360000 | 3360000 | 22954800 | 23520000 | 46474800 | 5
NA-GDS-APP | NA¦6103 | 5107950 | 5353800 | 5388300 | 5010750 | 5022450 | 5200050 | 5200050 | 5200050 | 5200050 | 5200050 | 5200050 | 5200050 | 25883250 | 36400350 | 62283600 | 5
NA-GDS-APP | NA¦6106 | 6991200 | 7154250 | 7221750 | 7010250 | 6842700 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 35220150 | 50400000 | 85620150 | 5
NA-GDS-DAT | NA¦6101 | 1556400 | 1632750 | 1698300 | 1722300 | 1905000 | 1920000 | 1984050 | 2047950 | 2112000 | 2176050 | 2239950 | 2304000 | 8514750 | 14784000 | 23298750 | 5
NA-GDS-DAT | NA¦6103 | 2539350 | 2543550 | 2451900 | 2455650 | 2511000 | 2560050 | 2560050 | 2560050 | 2560050 | 2560050 | 2560050 | 2560050 | 12501450 | 17920350 | 30421800 | 5
NA-GDS-GOV | NA¦6106 | 3115200 | 3145500 | 3088050 | 3262200 | 3193350 | 3199950 | 3199950 | 3199950 | 3199950 | 3199950 | 3199950 | 3199950 | 15804300 | 22399650 | 38203950 | 5
NA-GDS-GOV | NA¦6107 | 376200 | 372450 | 392850 | 398850 | 394200 | 384000 | 895950 | 895950 | 895950 | 895950 | 895950 | 895950 | 1934550 | 5759700 | 7694250 | 5
NA-GDS-GOV | NA¦6108 | 737100 | 732000 | 698700 | 717600 | 707100 | 720000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 3592500 | 2160000 | 5752500 | 5
NA-GDS-INF | NA¦6101 | 3933000 | 4003950 | 4143150 | 4048650 | 3985650 | 4000050 | 4000050 | 4000050 | 4000050 | 4000050 | 4000050 | 4000050 | 20114400 | 28000350 | 48114750 | 5
NA-GDS-INF | NA¦6102 | 1455600 | 1375050 | 1484550 | 1469100 | 1481400 | 1440000 | 1440000 | 1440000 | 1440000 | 1440000 | 1440000 | 1440000 | 7265700 | 10080000 | 17345700 | 5
NA-GDS-INF | NA¦6104 | 1891800 | 1893000 | 1841850 | 1933650 | 1834800 | 1920000 | 1920000 | 1920000 | 1920000 | 1920000 | 1920000 | 1920000 | 9395100 | 13440000 | 22835100 | 5
NA-GDS-INF | NA¦6105 | 2325150 | 2315100 | 2353500 | 2291400 | 2280000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 11565150 | 16800000 | 28365150 | 5
NA-GDS-INF | NA¦6106 | 5754750 | 5896350 | 5713800 | 6172200 | 6031650 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 29568750 | 42000000 | 71568750 | 5
NA-GDS-SEC | NA¦6101 | 2131200 | 2006250 | 1980300 | 2154150 | 2074950 | 2080050 | 2080050 | 2080050 | 2080050 | 2080050 | 2080050 | 2080050 | 10346850 | 14560350 | 24907200 | 5
NA-GDS-SEC | NA¦6103 | 2716950 | 2590500 | 2713200 | 2823450 | 2795250 | 2719950 | 2719950 | 2719950 | 2719950 | 2719950 | 2719950 | 2719950 | 13639350 | 19039650 | 32679000 | 5
EU-GDS-APP | EMEA¦7101 | 2000320 | 2047820 | 2044020 | 2125910 | 2175880 | 2100070 | 2100070 | 2100070 | 2100070 | 2100070 | 2100070 | 2100070 | 10393950 | 14700490 | 25094440 | 5
EU-GDS-APP | EMEA¦7103 | 3361480 | 3376490 | 3366800 | 3194090 | 3151910 | 3249950 | 3249950 | 3249950 | 3249950 | 3249950 | 3249950 | 3249950 | 16450770 | 22749650 | 39200420 | 5
EU-GDS-APP | EMEA¦7106 | 4354610 | 4357650 | 4527700 | 4639610 | 4615290 | 4499960 | 4499960 | 4499960 | 4499960 | 4499960 | 4499960 | 4499960 | 22494860 | 31499720 | 53994580 | 5
EU-GDS-DAT | EMEA¦7101 | 2394190 | 2392860 | 2421930 | 2524910 | 2484630 | 2550040 | 2589940 | 2630030 | 2669930 | 2710020 | 2749920 | 2790010 | 12218520 | 18689890 | 30908410 | 5
EU-GDS-DAT | EMEA¦7103 | 319960 | 319960 | 479940 | 639920 | 799900 | 1119993 | 1119993 | 1119993 | 1119993 | 1119993 | 1119993 | 1119993 | 2559680 | 7839951 | 10399631 | 5
EU-GDS-GOV | EMEA¦7106 | 1994240 | 1903230 | 1979230 | 1932870 | 1900570 | 1999940 | 1999940 | 1999940 | 1999940 | 1999940 | 1999940 | 1999940 | 9710140 | 13999580 | 23709720 | 5
EU-GDS-GOV | EMEA¦7107 | 231610 | 238260 | 243580 | 239970 | 235030 | 239970 | 559930 | 559930 | 559930 | 559930 | 559930 | 559930 | 1188450 | 3599550 | 4788000 | 5
EU-GDS-GOV | EMEA¦7108 | 449920 | 459230 | 431680 | 450110 | 437570 | 449920 | 149910 | 149910 | 149910 | 149910 | 149910 | 149910 | 2228510 | 1349380 | 3577890 | 5
EU-GDS-INF | EMEA¦7101 | 2521870 | 2554930 | 2394000 | 2523580 | 2579630 | 2500020 | 2500020 | 2500020 | 2500020 | 2500020 | 2500020 | 2500020 | 12574010 | 17500140 | 30074150 | 5
EU-GDS-INF | EMEA¦7102 | 915800 | 893760 | 869440 | 919030 | 881980 | 900030 | 900030 | 900030 | 900030 | 900030 | 900030 | 900030 | 4480010 | 6300210 | 10780220 | 5
EU-GDS-INF | EMEA¦7104 | 1245070 | 1182750 | 1183320 | 1242220 | 1218280 | 1200040 | 1200040 | 1200040 | 1200040 | 1200040 | 1200040 | 1200040 | 6071640 | 8400280 | 14471920 | 5
EU-GDS-INF | EMEA¦7105 | 1442290 | 1445520 | 1547170 | 1533870 | 1444760 | 1500050 | 1500050 | 1500050 | 1500050 | 1500050 | 1500050 | 1500050 | 7413610 | 10500350 | 17913960 | 5
EU-GDS-INF | EMEA¦7106 | 3893290 | 3784420 | 3680870 | 3747750 | 3606770 | 3750030 | 3750030 | 3750030 | 3750030 | 3750030 | 3750030 | 3750030 | 18713100 | 26250210 | 44963310 | 5
EU-GDS-SEC | EMEA¦7101 | 1265400 | 1284020 | 1250390 | 1341400 | 1276420 | 1299980 | 1299980 | 1299980 | 1299980 | 1299980 | 1299980 | 1299980 | 6417630 | 9099860 | 15517490 | 5
EU-GDS-SEC | EMEA¦7103 | 1704110 | 1753320 | 1679220 | 1755410 | 1691760 | 1699930 | 1699930 | 1699930 | 1699930 | 1699930 | 1699930 | 1699930 | 8583820 | 11899510 | 20483330 | 5

## Cost_Centers
cost_center_code | cost_center_name | region | function | sub_function | active
JP-GDS-APP | Japan GDS Applications | JP | GDS | Applications | Y
JP-GDS-INF | Japan GDS Infrastructure | JP | GDS | Infrastructure | Y
JP-GDS-DAT | Japan GDS Data | JP | GDS | Data | Y
JP-GDS-SEC | Japan GDS Security | JP | GDS | Security | Y
JP-GDS-GOV | Japan GDS Governance | JP | GDS | Governance | Y
NA-GDS-APP | North America GDS Applications | NA | GDS | Applications | Y
NA-GDS-INF | North America GDS Infrastructure | NA | GDS | Infrastructure | Y
NA-GDS-DAT | North America GDS Data | NA | GDS | Data | Y
NA-GDS-SEC | North America GDS Security | NA | GDS | Security | Y
NA-GDS-GOV | North America GDS Governance | NA | GDS | Governance | Y
EU-GDS-APP | EMEA GDS Applications | EMEA | GDS | Applications | Y
EU-GDS-INF | EMEA GDS Infrastructure | EMEA | GDS | Infrastructure | Y
EU-GDS-DAT | EMEA GDS Data | EMEA | GDS | Data | Y
EU-GDS-SEC | EMEA GDS Security | EMEA | GDS | Security | Y
EU-GDS-GOV | EMEA GDS Governance | EMEA | GDS | Governance | Y
JP-SLS-100 | Japan Sales Operations | JP | Sales | Sales Operations | Y
JP-RND-200 | Japan Research | JP | R&D | Research | Y

## Accounts
account_key | region | local_account_code | local_account_name | global_coa_code | global_coa_name | mgmt_category
JP¦5101 | JP | 5101 | Software & SaaS fees | G6100 | IT services | SG&A
JP¦5102 | JP | 5102 | Maintenance | G6110 | IT maintenance | SG&A
JP¦5103 | JP | 5103 | Outsourcing | G6120 | Outsourcing | SG&A
JP¦5104 | JP | 5104 | Telecom | G6130 | Telecom | SG&A
JP¦5105 | JP | 5105 | Depreciation | G6500 | Depreciation | Depreciation
JP¦5106 | JP | 5106 | Salaries | G5100 | Salaries | Personnel
JP¦5107 | JP | 5107 | Travel | G6300 | Travel | SG&A
JP¦5108 | JP | 5108 | Training | G6310 | Training | SG&A
NA¦6101 | NA | 6101 | Software & SaaS fees | G6100 | IT services | SG&A
NA¦6102 | NA | 6102 | Maintenance | G6110 | IT maintenance | SG&A
NA¦6103 | NA | 6103 | Outsourcing | G6120 | Outsourcing | SG&A
NA¦6104 | NA | 6104 | Telecom | G6130 | Telecom | SG&A
NA¦6105 | NA | 6105 | Depreciation | G6500 | Depreciation | Depreciation
NA¦6106 | NA | 6106 | Salaries | G5100 | Salaries | Personnel
NA¦6107 | NA | 6107 | Travel | G6300 | Travel | SG&A
NA¦6108 | NA | 6108 | Training | G6310 | Training | SG&A
EMEA¦7101 | EMEA | 7101 | Software & SaaS fees | G6100 | IT services | SG&A
EMEA¦7102 | EMEA | 7102 | Maintenance | G6110 | IT maintenance | SG&A
EMEA¦7103 | EMEA | 7103 | Outsourcing | G6120 | Outsourcing | SG&A
EMEA¦7104 | EMEA | 7104 | Telecom | G6130 | Telecom | SG&A
EMEA¦7105 | EMEA | 7105 | Depreciation | G6500 | Depreciation | Depreciation
EMEA¦7106 | EMEA | 7106 | Salaries | G5100 | Salaries | Personnel
EMEA¦7107 | EMEA | 7107 | Travel | G6300 | Travel | SG&A
EMEA¦7108 | EMEA | 7108 | Training | G6310 | Training | SG&A

## FX_Rates
fiscal_year | rate_type | currency | rate_to_jpy
2027 | BUDGET | JPY | 1
2027 | BUDGET | USD | 150
2027 | BUDGET | EUR | 160
2027 | BUDGET | GBP | 190

## Lists
region | currency | contract_type | employment_type | allocation_type | source_type | cost_category | rate_type | yes_no
JP | JPY | PREPAID | EMPLOYEE | COST_CENTER | MANUAL | SaaS / License | BUDGET | Y
NA | USD | MONTHLY | EXTERNAL | PROJECT | CONTRACT | Maintenance |  | N
EMEA | EUR | RATE_REF |  |  | ASSET | Outsourcing
| GBP |  |  |  | WORKFORCE | Cloud
Telecom
Hardware
Personnel
Depreciation
Travel & Training
Other