## Slide 1: IT Department Budget Guidelines: Supplement
IT Budget Transfer Essentials
November 2026 Kickoff
Notes: この資料は「IT部門向け予算ガイドライン」の追補で、来年度予算からの IT予算移管を、GDSの各チームが普段の業務の中で進めるときの拠り所です。予算移管はプロジェクトではなく、専用の体制も作りません。全社で決まっている方針は守り、それ以外の進め方は、カウンターパートの各ファンクションと合意して決めてください。

## Slide 2: About This Document
Explains the approach and handling of frequently asked topics on the budget transfer, clearly and without misunderstanding
Purpose
This document illustrates the approach and handling of topics often raised about the budget transfer. It adds the background that individual answers cannot easily convey, so that everyone understands it correctly.
Relation to Q&A list
Individual questions and answers are kept in the Q&A list. This document sets out the thinking behind them. Please refer to both as needed.
How to use
GDS transfer leads can use it when talking with their business counterparts, so both sides look at the same picture and align. It can also help you check your own understanding.
Updates
We will add to and update this document as questions come in. Please see the revision history for changes.

## Slide 3: Revision History
Date | Changes
2026/11/02 | First edition published

## Slide 4: Contents
Page | Topic | Summary
p.5 | November–December Schedule | Tasks for Assigned BPs and S&G (FinanceBP), milestones and definitions of done
p.6 | Roles After the Transfer (RACI) | Roles of GDS and the Functions in the IT domain
p.7 | Alternative: Roles for Function-Specific Cases | When roles switch for cases confined to one Function
p.8 | Fixed Assets Move to GDS | Transfer timing and approach by asset status

## Slide 5: November–December Schedule (Indicative)
November
December
January onward
Milestones
Start
Outlook report
Work complete
Approval
Transfer
Assigned BP
Operating expense budget transfer
① Identify budgets to transfer, using the interview sheet
② Enter them in the budget sheet (remove out-of-scope, add missing)
③ Keep status updated; report completion outlook at end of Nov
④ Take over contracts, ordering, etc. (start agreed with counterpart)
Fixed asset transfer
① Review the asset register; set timing (with transfer / later)
② Update the review status in the register
S&G (FinanceBP)
Provide the fixed asset register to Assigned BPs
Track overall progress via budget sheet and register status (ongoing)
Report transfer scope based on end-of-Nov outlook
Prepare approval request (units, pre-approvals, stakeholders)
Submit approval request; share result with Assigned BPs
Transfer fixed assets and depreciation step by step
Definition of done (end of December)
① Budgets to transfer are agreed with the current owner
② Budgets to transfer are fully listed in the budget sheet
③ Handover of the related work has started
Definition of done (end of December)
① Assets to transfer and their timing are identified
② Treatment of these assets from next year is understood
Definition of done (end of December)
① Transfer approval is granted
② Result is shared with Assigned BPs
③ Fixed asset transfer has started
Orders needed this year can proceed where possible, without waiting for the transfer
Contract name changes can be made at a suitable time; they need not coincide with the transfer
Notes: 11月と12月の進め方の目安です。担当BPは、ヒアリングシートを基に移管元と合意し、業務マニュアルや契約書、過去の記録を基に引き継ぎ、稟議申請の時点で完了を報告します。期間を通して、進捗管理表を随時更新し、問題が起きたとき、または起きそうなときは報告・相談してください。ゴールは、S&Gにとっては移管の稟議が承認されていること、担当BPにとっては移管後の業務を開始できる状態にあることです。どちらも、その状態に行くための材料がそろっている必要があります。

## Slide 6: Roles After the Transfer (RACI)
In the IT domain, GDS and the Functions work together, with GDS leading to balance enterprise-wide and local needs
Cases confined to one Function continue to be led by that Function, with GDS in support
Business strategy
Business
Set business direction and state what IT should deliver to achieve it
IT strategy
IT-led
Set IT investment policy and enterprise platforms to realize the business direction
System requirements
IT-led
Define functional, non-functional and transition requirements
Solution
IT-led
Choose the means (SaaS, package, custom build) that fits requirements and policy
Vendor
IT-led
Compare proposals and quotes to choose suppliers; manage performance and risk
Business requirements
Business
Clarify desired business outcomes; set requirements and priorities
Business benefits
Business
Measure KPI results to confirm benefits and identify blockers
Direction & issues
KPI results
Expectations of IT
Architecture policy
(technology, data, security)
Requirements & priorities
Specs
RFP
Live system
Development standards
(SDLC, CSV)
Sourcing policy
(in-house, outsourced, offshore/nearshore)
Business
R, A: Functions
IT-led
R, A: GDS C: Functions
IT-led domain
GDS is responsible for the indirect work tied to transferred budgets (budget, contracts, ordering and payment)
Notes: 移管後の役割分担です。箱は領域、矢印の上に書いたのが行為です。ビジネス戦略から要求を明確にしてビジネス要件を定め、受け入れと効果測定の結果を評価して戦略を見直すのは各ファンクションです。ビジネス戦略を受けて IT戦略を策定し、その方針をソリューションに適用すること、非機能要件をシステム要件に示すこと、ソーシングの方針をベンダーに示すこと、ビジネス要件をシステム要件に落とす要件定義、ソリューション選定、ベンダー選定は、GDSがリードし、各ファンクションの助言のもとで GDSが決定します。ただし、ある部門に固有で、他への影響が一切ないシステムは、この限りではありません。IT財務管理、契約管理、サービス品質管理は GDSが担います。分担の細部と GDSが担い始める時期は、案件ごとに合意文書で確定してください。

## Slide 7: Alternative: Roles for Function-Specific Cases (RACI)
Business strategy
Business
Set business direction and state what IT should deliver to achieve it
IT strategy
IT-led
Set IT investment policy and enterprise platforms to realize the business direction
System requirements
Business-led
Define functional, non-functional and transition requirements
Solution
Business-led
Choose the means (SaaS, package, custom build) that fits requirements and policy
Vendor
Business-led
Compare proposals and quotes to choose suppliers; manage performance and risk
Business requirements
Business
Clarify desired business outcomes; set requirements and priorities
Business benefits
Business
Measure KPI results to confirm benefits and identify blockers
Direction & issues
KPI results
Expectations of IT
Architecture policy
(technology, data, security)
Requirements & priorities
Specs
RFP
Live system
Development standards
(SDLC, CSV)
Sourcing policy
(in-house, outsourced, offshore/nearshore)
Business
R, A: Functions
IT-led
R, A: GDS C: Functions
Function-led domain
Where Function-led work runs more smoothly, carry on as before, but keep looking through the system lens
Is the same data entered twice? Are reports or data from elsewhere checked or fixed by hand? Does another Function contract the same tool?
Business-led
R, A: Functions C: GDS

## Slide 8: Fixed Assets Move to GDS
All fixed assets from in-scope IT investments move to GDS. Timing depends on each asset's status at transfer
FinanceBP reassigns the depreciation budget with the assets; after transfer, depreciation is booked to GDS
Asset status
To Dec 2026 (before transfer)
From Jan 1, 2027 (after transfer)
① Existing assets
Acquired and being depreciated (incl. zero book value)
② To be acquired
Under construction; capitalized after transfer (with or without CIP)
③ Future assets
Budgeted or expected; started after transfer
④ Existing + upgrade
Existing asset being upgraded; upgrade capitalized after transfer
⑤ Planned disposal/impairment
Assets planned for disposal or impairment
Current owner
GDS
Move on transfer date
Current owner (project continues)
GDS
Move when capitalized
Budget: current owner
Budget: GDS
Budget transfer
GDS (from CIP)
Held by GDS from start
Base asset: current owner
GDS
Base asset moves when the upgrade is capitalized
Upgrade (in progress): current owner
GDS
This year: current owner
Approved
Dispose / impair
Next year on: current owner
GDS (moves with existing assets)
Dispose / impair
Select assets to transfer from the register provided by Finance and return it; FinanceBP handles the transfer